## Sheet1
UTC TIME REFERENCE | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-03-13 17:11 | 0:00 |  | 27.8 | 355.7 | 2938.8 | [6 empty] | Aposelene | [6 empty] | Downlinking SSDR Segment 6 (orbit 103)
LHG104 Script
1994-03-13 17:21 | 0:10 | 0 | [10 empty] | Msg "WRNG: Omni/2k in 1 min.."; Open either ST door if closed; SSDR to IDLE | [5 empty] | Stop data dump
1994-03-13 17:22 | 0:11 | 60 | [10 empty] | Switch to 2 kbps bypass mode
1994-03-13 17:23 | 0:12 | 60 | [10 empty] | Switch to omni antennas
1994-03-13 17:24 | 0:13 | 60 | [10 empty] | Slew ST-B to Moon (GNC12M104); Record in SSDR Segment 7 | [5 empty] | Slew ST-B to Moon (inertial pointing) SSDR Segment 7
1994-03-13 17:24 | 0:13 |  | 20 | 355.6 | 2913.3 | [6 empty] | N20D
1994-03-13 17:27 | 0:15 |  | 18.5 | 355.6 | 2903.1 | [6 empty] | INPM | [6 empty] | Enter penumbra
1994-03-13 17:27 | 0:16 | [11 empty] | Select ST-A | [5 empty] | Ground Command
1994-03-13 17:28 | 0:16 |  | 18 | 355.6 | 2898.5 | [6 empty] | INUM | [6 empty] | Enter umbra
1994-03-13 17:30 | 0:19 | [11 empty] | Begin imaging with ST-B (DHUSEL23) | [5 empty] | Ground Command Script error left this command out, also wrong table
1994-03-13 17:31 | 0:19 | 372 | [10 empty] | Inertial pointing w/ quaternion table (STK_104MOON003.QTB) | [5 empty] | Start pointing using quaternion tables
1994-03-13 17:31 | 0:20 | [11 empty] | Stop imaging - select ST-B; Upload SEQ_ZOOK.UMI into SEQT 23; Select DHU SEQT 23 | [5 empty] | Ground Command START LHG SUNSET IMAGING: Uncompressed star tracker 'B' image every 10 seconds
1994-03-13 17:41 | 0:29 | 600 | [10 empty] | Use QTable STK_104MOON004.QTB | [5 empty] | IMAGES OVEREXPOSED!
1994-03-13 17:41 | 0:29 |  | 10 | 355.5 | 2810.6 | [6 empty] | N10D
1994-03-13 17:51 | 0:39 | 600 | [10 empty] | Use QTable STK_104MOON005.QTB
1994-03-13 17:53 | 0:42 | [11 empty] | SSDR to IDLE | [5 empty] | Ground Command
1994-03-13 17:54 | 0:42 | 180 | [10 empty] | Stop imaging - select ST-B; SA step rate to HI; Slew HGA to Earth (GNC13EARTH) | [5 empty] | END LHG IMAGING
End LHG104 Script
1994-03-13 17:56 | 0:45 |  | 0 | 355.4 | 2641.7 | [6 empty] | Equator - D
1994-03-13 17:57 | 0:46 | [11 empty] | Switch to HGA; Switch to DHU mode @ 128 kbps | [5 empty] | Ground Command
1994-03-13 18:02 | 0:51 | [11 empty] | Resume downlinking SSDR Segment 6 | [5 empty] | Ground Command
1994-03-13 18:10 | 0:59 |  | -10 | 355.3 | 2425.6 | [6 empty] | S10D
1994-03-13 18:22 | 1:11 |  | -20 | 355.2 | 2183.1 | [6 empty] | S20D
1994-03-13 18:30 | 1:19 |  | -27 | 355.2 | 2008 | [6 empty] | OUTUM | [6 empty] | Exit umbra
1994-03-13 18:31 | 1:20 |  | -27.7 | 355.2 | 1989.4 | [6 empty] | OUTPM | [6 empty] | Exit penumbra
Standard Prep1 Script
1994-03-13 18:33 | 1:21 | 0 | [10 empty] | NIR camera & cryocooler ON; Solar Arrays mode to AUTO
End Prep1 Script
1994-03-13 18:34 | 1:22 |  | -30 | 355.1 | 1932.5 | [6 empty] | S30D
1994-03-13 18:43 | 1:32 |  | -40 | 355.1 | 1688.1 | [6 empty] | S40D
Standard Prep2 Script
1994-03-13 18:46 | 1:35 | 0 | [10 empty] | LWIR camera & cryocooler ON; Laser heater ON; Open sensor door if closed
End Prep2 Script
1994-03-13 18:47 | 1:36 | [11 empty] | Downlink SSSDR 7 | [5 empty] | Ground Command
#VALUE!
1994-03-13 18:51 | 1:40 | 0 | [10 empty] | Msg "WRNG: Omni/2k in 1 min.."
1994-03-13 18:52 | 1:40 |  | -50 | 355.1 | 1459.3 | [6 empty] | S50D
1994-03-13 18:52 | 1:41 | 60 | [10 empty] | SSDR to IDLE; Switch to 2 kbps bypass mode | [5 empty] | Stop SSDR data dump
1994-03-13 18:53 | 1:42 | 60 | [10 empty] | Switch to omni antennas
1994-03-13 18:54 | 1:43 | 60 | [10 empty] | Select ST-A; Set SA step rate to HI; Slew s/c sensors to Crux (ACSMode=StarPointing, Index=3) | [5 empty] | Using ST-A again Slew to Crux
1994-03-13 18:55 | 1:43 | 30 | [10 empty] | UV & HR cameras ON
1994-03-13 18:59 | 1:47 |  | -60 | 355.1 | 1252 | [6 empty] | S60D
1994-03-13 19:04 | 1:52 | 545 | [10 empty] | Initialize filters (DHU SEQT 28); Record in SSDR Segment 1; Load lunar dark exposure tables | [5 empty] | Start SSDR in Segment 1
1994-03-13 19:04 | 1:53 | 25 | [10 empty] | Perform NIR imaging (DHU SEQT 31) | [5 empty] | Dark Field imaging starts
1994-03-13 19:04 | 1:53 | 15 | [10 empty] | Stop imaging - select ST-A
1994-03-13 19:05 | 1:54 |  | -70 | 355.2 | 1068.8 | [6 empty] | S70D
1994-03-13 19:06 | 1:55 | 105 | [10 empty] | Perform LWIR imaging (DHU SEQT 25)
1994-03-13 19:06 | 1:55 | 15 | [10 empty] | Perform NIR imaging (DHU SEQT 31)
1994-03-13 19:06 | 1:55 | [9 empty] | MAD | LOS
1994-03-13 19:07 | 1:55 | 15 | [10 empty] | #VALUE! | [5 empty] | Slew to nadir (inertial pointing)
1994-03-13 19:07 | 1:56 | 30 | [10 empty] | Laser Power ON
#VALUE!
1994-03-13 19:11 | 2:00 |  | -80 | 355.6 | 910.4 | [6 empty] | S80D
#VALUE!
1994-03-13 19:15 | 2:03 | 0 | [10 empty] | Initialize filters (DHU SEQT 28)
1994-03-13 19:15 | 2:03 | 5 | [10 empty] | Park opaque filter on HiRes (DHU SEQT 27); Load exposure table LUNARZ85S | [5 empty] | HiRes imaging off because of LHG observation time
1994-03-13 19:16 | 2:04 | 55 | [10 empty] | Switch to lunar mapping mode (ACSMode=LunarMapping); Start imaging (DHU SEQT 9) | [5 empty] | START MAPPING
1994-03-13 19:16 | 2:05 |  | -89.8 | 81.7 | 776.3 | [6 empty] | South Pole
1994-03-13 19:17 | 2:05 | 60 | [9 empty] | MAXS | Set SA step rate to LO
1994-03-13 19:17 | 2:05 |  | -88.6 | 168.2 | 759.4 | [6 empty] | LDAWN
1994-03-13 19:21 | 2:09 |  | -80 | 173.7 | 665.2 | [6 empty] | S80A
1994-03-13 19:21 | 2:10 | 277 | [9 empty] | S80A | Load exposure table LUNARZ75S; Select DHU SEQT 3
1994-03-13 19:25 | 2:14 |  | -70 | 174.1 | 576.1 | [6 empty] | S70A
1994-03-13 19:26 | 2:14 | 255 | [9 empty] | S70A | Load exposure table LUNARZ65S; Select DHU SEQT 4
1994-03-13 19:29 | 2:17 |  | -60 | 174.3 | 507.4 | [6 empty] | S60A
1994-03-13 19:29 | 2:18 | 238 | [9 empty] | S60A | Load exposure table LUNARZ55S; Select DHU SEQT 6
1994-03-13 19:33 | 2:21 |  | -50 | 174.3 | 458.2 | [6 empty] | S50A
1994-03-13 19:33 | 2:22 | 226 | [9 empty] | S50A | Record in SSDR Segment 2; Load exposure table LUNARZ45S; Select DHU SEQT 5 | [5 empty] | SSDR Segment 2
1994-03-13 19:33 | 2:22 | [9 empty] | GDS | MLOSM
1994-03-13 19:33 | 2:22 | [9 empty] | PMK | MLOSM | [6 empty] | Enter occultation
1994-03-13 19:36 | 2:25 |  | -40 | 174.3 | 427.5 | [6 empty] | S40A
1994-03-13 19:37 | 2:25 | 218 | [9 empty] | S40A | Load exposure table LUNARZ35S
1994-03-13 19:40 | 2:28 |  | -30 | 174.3 | 414.8 | [6 empty] | S30A
1994-03-13 19:40 | 2:29 | 214 | [9 empty] | S30A | Load exposure table LUNARZ25S
1994-03-13 19:41 | 2:29 |  | -27.8 | 174.3 | 414.3 | [6 empty] | Periselene
1994-03-13 19:43 | 2:32 |  | -20 | 174.3 | 419.8 | [6 empty] | S20A
1994-03-13 19:44 | 2:33 | 213 | [9 empty] | S20A | Load exposure table LUNARZ15S
1994-03-13 19:47 | 2:36 |  | -10 | 174.3 | 442.6 | [6 empty] | S10A
1994-03-13 19:48 | 2:36 | 215 | [9 empty] | S10A | Load exposure table LUNARZ05S; Select DHU SEQT 6
1994-03-13 19:51 | 2:39 |  | 0 | 174.3 | 483.7 | [6 empty] | Equator - A
1994-03-13 19:51 | 2:40 | 222 | [9 empty] | MEQA | Record in SSDR Segment 3; Load exposure table LUNARZ05N; Select DHU SEQT 7 | [5 empty] | SSDR Segment 3
1994-03-13 19:55 | 2:43 |  | 10 | 174.3 | 543.7 | [6 empty] | N10A
1994-03-13 19:55 | 2:44 | 233 | [9 empty] | N10A | Load CEQ_08U.UMI into SEQT 8; Load exposure table LUNARZ15N; Select DHU SEQT 8 | [5 empty] | IR and UV uncompressed
1994-03-13 19:59 | 2:47 |  | 20 | 174.3 | 623.8 | [6 empty] | N20A
1994-03-13 19:59 | 2:48 | 247 | [9 empty] | N20A | Load exposure table LUNARZ25N; Select DHU SEQT 9 | [5 empty] | Resume compression
1994-03-13 20:00 | 2:49 | 60 | [10 empty] | Laser power OFF
1994-03-13 20:03 | 2:52 |  | 30 | 174.3 | 725 | [6 empty] | N30A
1994-03-13 20:04 | 2:52 | 206 | [9 empty] | N30A | Load exposure table LUNARZ35N; Select DHU SEQT 10
1994-03-13 20:08 | 2:57 |  | 40 | 174.3 | 848.9 | [6 empty] | N40A
1994-03-13 20:09 | 2:57 | 292 | [9 empty] | N40A | Record in SSDR Segment 4; Load exposure table LUNARZ45N; Select DHU SEQT 11 | [5 empty] | SSDR Segment 4
1994-03-13 20:11 | 2:59 | [9 empty] | GDS | MAOSM | [6 empty] | Exit occultation
1994-03-13 20:11 | 2:59 | [9 empty] | PMK | MAOSM
1994-03-13 20:13 | 3:02 |  | 50 | 174.3 | 996.6 | [6 empty] | N50A
1994-03-13 20:14 | 3:03 | 325 | [9 empty] | N50A | Load exposure table LUNARZ55N; Select DHU SEQT 12
1994-03-13 20:20 | 3:08 |  | 60 | 174.4 | 1169 | [6 empty] | N60A
1994-03-13 20:20 | 3:09 | 365 | [9 empty] | N60A | Load exposure table LUNARZ65N; Select DHU SEQT 13
1994-03-13 20:26 | 3:15 |  | 70 | 174.4 | 1366 | [6 empty] | N70A
1994-03-13 20:27 | 3:16 | 414 | [9 empty] | N70A | Load exposure table LUNARZ75N; Select DHU SEQT 14
1994-03-13 20:34 | 3:23 |  | 80 | 174.8 | 1585.9 | [6 empty] | N80A
1994-03-13 20:35 | 3:23 | 473 | [9 empty] | N80A | Load exposure table LUNARZ85N; Select DHU SEQT 15
1994-03-13 20:36 | 3:24 | 60 | [10 empty] | Load DEQ_08.UMI into SEQT 8 | [5 empty] | Restore compressed SEQT 8
#VALUE!
Standard Post Script
1994-03-13 20:37 | 3:25 | 0 | [10 empty] | Park filters (DHU SEQT 27); Set SA step rate to HI; Select ST-B; Slew s/c sensors to Vega (GNC12VEGA); Laser power OFF; Load dark images exposure table | [5 empty] | Timeline error: this script should start AFTER North Pole Slew to Vega (inertial pointing)
1994-03-13 20:43 | 3:32 |  | 89.8 | 261.6 | 1824.2 | [6 empty] | North Pole
1994-03-13 20:45 | 3:33 |  | 88.6 | 347.3 | 1858.8 | [6 empty] | LDUSK
1994-03-13 20:47 | 3:36 | 600 | [10 empty] | Perform UVO Imaging (DHU SEQT 29) | [5 empty] | No data because duration was 15 tics instead of 15 seconds
1994-03-13 20:47 | 3:36 | 0 | [10 empty] | Perform LWIR imaging (DHU SEQT 25) | [5 empty] | Dark Field imaging starts
1994-03-13 20:47 | 3:36 | 15 | [10 empty] | Perform NIR imaging (Select DHU SEQT 31)
1994-03-13 20:47 | 3:36 | 15 | [10 empty] | Perform HiRes Imaging (DHU SEQT 30) | [5 empty] | Radiometric imaging
1994-03-13 20:48 | 3:36 | 7 | [10 empty] | Stop imaging - select ST-B; UV & HR cameras OFF; IR cameras & cryocoolers OFF; Slew s/c HGA to Earth (ACSMode=EarthPointing, Center) | [5 empty] | Slew HGA to Earth
1994-03-13 20:54 | 3:42 |  | 80 | 352.9 | 2073.7 | [6 empty] | N80D
1994-03-13 20:54 | 3:42 | 360 | [10 empty] | Switch to HGA | [5 empty] | READY FOR DATA DUMP
End Post Script
1994-03-13 20:56 | 3:45 | [11 empty] | Switch to DHU mode @ 128 kbps | [5 empty] | Ground Command
1994-03-13 20:59 | 3:48 | [11 empty] | Resume downlinking SSDR Segment 7 | [5 empty] | Ground Command Not all data dumped due to overexposure of images
1994-03-13 21:05 | 3:54 | [11 empty] | Downlink SSDR Segment 1 | [5 empty] | Ground Command
1994-03-13 21:06 | 3:54 |  | 70 | 353.2 | 2321.8 | [6 empty] | N70D
1994-03-13 21:19 | 4:08 |  | 60 | 353.3 | 2551.7 | [6 empty] | N60D
1994-03-13 21:26 | 4:15 | [11 empty] | Uplink ST exposure table (EXPDAY5.UMI) | [5 empty] | Ground Command
1994-03-13 21:34 | 4:22 |  | 50 | 353.2 | 2743.5 | [6 empty] | N50D
1994-03-13 21:44 | 4:33 | [11 empty] | Downlink SSDR Segment 2 | [5 empty] | Ground Command
1994-03-13 21:50 | 4:38 |  | 40 | 353.1 | 2876.8 | [6 empty] | N40D
1994-03-13 22:06 | 4:55 |  | 30 | 353 | 2935.6 | [6 empty] | N30D
1994-03-13 22:10 | 4:58 |  | 27.8 | 353 | 2937.6 | [6 empty] | Aposelene