## Sheet1
UTC TIME REFERENCE | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-04-20 08:32 | 0:00 |  | -27.8 | 223.3 | 2941.3 | [6 empty] | Aposelene | [6 empty] | Downlinking SSDR Segment 3 (orbit 284)
1994-04-20 08:36 | 0:04 |  | -30 | 223.3 | 2939.3 | [6 empty] | S30D
1994-04-20 08:51 | 0:19 | [11 empty] | SSDR to IDLE - downlink complete | [5 empty] | Ground Command
1994-04-20 08:52 | 0:20 |  | -40 | 223.2 | 2880.2 | [6 empty] | S40D
1994-04-20 08:55 | 0:23 |  | -41.5 | 223.2 | 2864.3 | [5 empty] | GDS | LOS
Standard Prep1 Script
1994-04-20 09:07 | 0:35 | 0 | [10 empty] | NIR camera & cryocooler ON; SA mode to AUTO
End Prep1 Script
1994-04-20 09:08 | 0:36 |  | -50 | 223.2 | 2746.3 | [6 empty] | S50D
1994-04-20 09:23 | 0:51 |  | -60 | 223.2 | 2553.7 | [6 empty] | S60D
Standard Prep2 Script
1994-04-20 09:32 | 1:00 | 0 | [10 empty] | Laser heater ON; Open sensor door if closed
End Prep2 Script
1994-04-20 09:36 | 1:04 |  | -70 | 223.4 | 2323 | [6 empty] | S70D
#VALUE!
1994-04-20 09:43 | 1:11 | 0 | [10 empty] | Msg "WARNING: 2kbps in 1 min.."
1994-04-20 09:43 | 1:11 | 25 | [10 empty] | LWIR camera and cryocooler ON
1994-04-20 09:44 | 1:12 | 35 | [10 empty] | SSDR to IDLE; Switch to 2 kbps bypass mode
1994-04-20 09:45 | 1:13 | 60 | [10 empty] | Switch to omni antennas
1994-04-20 09:46 | 1:14 | 60 | [10 empty] | Select ST-B; Set SA step rate to HI; Slew s/c sensors to Crux (ACSMode=StarPointing, Index=3) | [5 empty] | Slew to Crux
1994-04-20 09:48 | 1:16 |  | -80 | 224.2 | 2074.1 | [6 empty] | S80D
1994-04-20 09:52 | 1:20 | 360 | [10 empty] | Initialize filters (DHU SEQT 27); Record in SSDR Segment 4; Load Crux exposure table (LUNCRUX) | [5 empty] | Start SSDR in Segment 4
1994-04-20 09:52 | 1:20 | 40 | [10 empty] | Perform NIR imaging (DHU SEQT 31) | [5 empty] | Dark field imaging
1994-04-20 09:52 | 1:21 | 15 | [10 empty] | #VALUE! | [5 empty] | Slew sensors to nadir at South Pole (inertial pointing)
1994-04-20 09:54 | 1:22 | 90 | [10 empty] | UV & HR cameras ON
#VALUE!
#VALUE!
1994-04-20 09:57 | 1:26 | 0 | [10 empty] | Initialize filters (DHU SEQT 28); Load exposure table LUNARZ85S; Load exposure table LUNARH85S
1994-04-20 09:58 | 1:26 | 30 | [10 empty] | Switch to lunar mapping mode (ACSMode=LunarMapping); Start Imaging (DHU SEQT 21) | [5 empty] | START MAPPING
1994-04-20 09:58 | 1:27 | 30 | -89.7 | 311.5 | 1824.3 | [6 empty] | South Pole | Set SA step rate to LO
1994-04-20 09:59 | 1:27 |  | -89.1 | 22.3 | 1803.4 | [6 empty] | LDAWN
1994-04-20 10:08 | 1:36 | 544 | -80 | 40.5 | 1585.2 | [6 empty] | S80A | Load exposure table LUNARZ75S; Load exposure table LUNARH75S; Select DHU SEQT 20
1994-04-20 10:15 | 1:43 | 474 | -70 | 41.4 | 1364.9 | [6 empty] | S70A | Load KEQ_19U.UMI into SEQT 19; Load exposure table LUNARZ65S; Load exposure table LUNARH65S; Select DHU SEQT 19 | [5 empty] | UV and IR uncompressed
1994-04-20 10:18 | 1:46 | 165.6 | [10 empty] | #VALUE! | [5 empty] | Slew to South Pole for oblique viewing Resume compression
1994-04-20 10:22 | 1:50 | 248.4 | -60 | 41.6 | 1167.5 | [6 empty] | S60A | Load exposure table LUNARZ55S; Load exposure table LUNARH55S; Select DHU SEQT 12
1994-04-20 10:23 | 1:51 | 60 | [10 empty] | Record in SSDR Segment 5 | [5 empty] | SSDR Segment 5
1994-04-20 10:28 | 1:56 | 305 | -50 | 41.7 | 994.9 | [6 empty] | S50A | Load exposure table LUNARZ45S; Select DHU SEQT 11 | [5 empty] | Stop HiRes imaging
1994-04-20 10:33 | 2:01 | 282 | [10 empty] | Laser Power ON
1994-04-20 10:34 | 2:02 | 42 | -40 | 41.8 | 847 | [6 empty] | S40A | Switch to lunar mapping mode (ACSMode=LunarMapping); Load exposure table LUNARZ35S; Select DHU SEQT 10 | [5 empty] | Resume nadir mapping
1994-04-20 10:39 | 2:07 | 292 | -30 | 41.8 | 723 | [6 empty] | S30A | Load exposure table LUNARZ25S; Select DHU SEQT 9
1994-04-20 10:43 | 2:11 | 266 | -20 | 41.9 | 621.6 | [6 empty] | S20A | Load KEQ_03H.UMI into SEQT 3; Load exposure table LUNARZ15S; Load exposure table LUNARH15S; Select DHU SEQT 3 | [5 empty] | HiRes Color Burst 20s to 15s
1994-04-20 10:45 | 2:13 | 123 | [10 empty] | Stop all imaging; Load exposure table LUNARZ15S; Load KEQ_03.UMI into SEQT 3; Select DHU SEQT 3 | [5 empty] | Restore original SEQT 3
1994-04-20 10:47 | 2:15 | 124 | -10 | 41.9 | 541.5 | [6 empty] | S10A | Load exposure table LUNARZ05S; Select DHU SEQT 7
1994-04-20 10:51 | 2:19 | 232 | 0 | 41.9 | 481.4 | [6 empty] | Equator - A | Load exposure table LUNARZ05N; Select DHU SEQT 6
1994-04-20 10:55 | 2:23 | 222 | 10 | 41.9 | 440.3 | [6 empty] | N10A | Load exposure table LUNARZ15N; Select DHU SEQT 5
1994-04-20 10:58 | 2:26 | 215 | 20 | 41.9 | 417.5 | [6 empty] | N20A | Load exposure table LUNARZ25N
1994-04-20 11:01 | 2:29 |  | 27.8 | 42 | 412 | [6 empty] | Periselene
1994-04-20 11:02 | 2:30 | 213 | 30 | 42 | 412.5 | [6 empty] | N30A | Load exposure table LUNARZ35N
1994-04-20 11:05 | 2:34 | 213 | 40 | 42 | 425.2 | [6 empty] | N40A | Load exposure table LUNARZ45N
1994-04-20 11:09 | 2:37 | 218 | 50 | 42.1 | 455.9 | [6 empty] | N50A | Load exposure table LUNARZ55N; Load exposure table LUNARH55N; Select DHU SEQT 6 | [5 empty] | Resume HiRes imaging
1994-04-20 11:13 | 2:41 | 226 | 60 | 42.2 | 505.2 | [6 empty] | N60A | Load exposure table LUNARZ65N; Load exposure table LUNARH65N; Select DHU SEQT 4
1994-04-20 11:14 | 2:42 | 60 | [10 empty] | Record in SSDR Segment 6 | [5 empty] | SSDR Segment 6
1994-04-20 11:17 | 2:45 | 178 | 70 | 42.5 | 573.9 | [6 empty] | N70A | Load exposure table LUNARZ75N; Load exposure table LUNARH75N; Select DHU SEQT 17
1994-04-20 11:21 | 2:49 | 254 | 80 | 43.3 | 663.1 | [6 empty] | N80A | Load exposure table LUNARZ85N; Load exposure table LUNARH85N; Select DHU SEQT 16 | [5 empty] | Stop laser imaging
1994-04-20 11:22 | 2:50 | 30 | [10 empty] | Laser power OFF
1994-04-20 11:22 | 2:50 | 30 | [10 empty] | Load KEQ_19.UMI into SEQT 19 | [5 empty] | Restore original SEQT 19
#VALUE!
1994-04-20 11:26 | 2:54 |  | 89.7 | 134.2 | 774.3 | [6 empty] | North Pole
1994-04-20 11:26 | 2:54 |  | 89.1 | 201.9 | 784.5 | [6 empty] | LDUSK
#VALUE!
1994-04-20 11:28 | 2:56 | 0 | [10 empty] | Stop Imaging - select ST-B
1994-04-20 11:28 | 2:56 | 5 | [10 empty] | #VALUE! | [5 empty] | Slew sensors to Earth (inertial pointing) with waitwhileslew
1994-04-20 11:31 | 2:59 |  | 80 | 219.8 | 908.4 | [6 empty] | N80D
#VALUE! | #VALUE! | #VALUE! | [10 empty] | Load EARTH exposure table (EARTH_VIEW_ZAXIS)
1994-04-20 11:31 | 2:59 | 15 | [10 empty] | Select DHU SEQT 23 | [5 empty] | Earth imaging w/color HiRes
#VALUE! | #VALUE! | 15 | [10 empty] | Stop imaging - select ST-B
#VALUE! | #VALUE! | 5 | [10 empty] | Slew s/c sensors to Vega (VEGAGNC12) | [5 empty] | Slew to Vega (inertial pointing)
#VALUE! | #VALUE! | 30 | [10 empty] | Park opaque filter on HiRes (DHU SEQT 27)
#VALUE! | #VALUE! | 15 | [10 empty] | Select ST-B; Activate waitwhileslew for 320 sec
#VALUE! | #VALUE! | #VALUE! | [10 empty] | Set SA mode to MANUAL; Load Vega exposure tables (LUNVEGA)
1994-04-20 11:35 | 3:03 | 60 | [10 empty] | Perform LWIR imaging (DHU SEQT 25) | [5 empty] | Start calibration imaging
#VALUE! | #VALUE! | 12 | [10 empty] | Perform NIR imaging (DHU SEQT 31)
#VALUE! | #VALUE! | 6 | [10 empty] | Load exposure table LUNIRDKS1
#VALUE! | #VALUE! | 6 | [10 empty] | Load exposure table LUNIRDKS2
#VALUE! | #VALUE! | 6 | [10 empty] | Perform UV0 imaging (DHU SEQT 29)
#VALUE! | #VALUE! | 12 | [10 empty] | Perform HiRes imaging (DHU SEQT 30)
1994-04-20 11:36 | 3:05 |  | 70 | 220.7 | 1067.1 | [6 empty] | N70D
#VALUE! | #VALUE! | 30 | [10 empty] | Stop imaging - select ST-B; Set SA mode to AUTO; UV & HR cameras OFF; IR cameras & cryocoolers OFF; Slew s/c HGA to Earth (ACSMode=EarthPointing, Center); Activate waitwhileslew for 360 sec | [5 empty] | Slew HGA to Earth with active waitwhileslew
1994-04-20 11:41 | 3:09 | #VALUE! | [10 empty] | Switch to HGA | [5 empty] | READY FOR DATA DUMP - Time approximate
#VALUE!
1994-04-20 11:42 | 3:10 | [11 empty] | Auxiliary oscillator B ON; Switch to DHU mode @ 128 kbps | [5 empty] | Ground Command
1994-04-20 11:43 | 3:11 |  | 60 | 220.9 | 1250.6 | [6 empty] | N60D
1994-04-20 11:50 | 3:18 |  | 50 | 221 | 1458.3 | [6 empty] | N50D
1994-04-20 11:51 | 3:19 | [11 empty] | Downlink SSDR Segment 4 | [5 empty] | Ground Command
1994-04-20 11:54 | 3:22 | [11 empty] | Uplink and schedule L286 scripts | [5 empty] | Ground Command
1994-04-20 11:59 | 3:27 |  | 40 | 221 | 1687.5 | [6 empty] | N40D
1994-04-20 12:06 | 3:34 | [11 empty] | Downlink SSDR Segment 5 | [5 empty] | Ground Command
1994-04-20 12:08 | 3:36 |  | 30 | 221 | 1932.6 | [6 empty] | N30D
1994-04-20 12:19 | 3:47 |  | 20 | 221 | 2183.9 | [6 empty] | N20D
1994-04-20 12:32 | 4:00 |  | 10 | 220.9 | 2427.1 | [6 empty] | N10D
1994-04-20 12:46 | 4:14 |  | 0 | 220.8 | 2643.8 | [6 empty] | Equator - D
1994-04-20 13:01 | 4:29 |  | -10 | 220.8 | 2813.2 | [6 empty] | S10D
1994-04-20 13:08 | 4:36 | [11 empty] | Uplink KEQ_04.UMI and load into SEQT 4 | [5 empty] | Ground Command - corrected table
1994-04-20 13:12 | 4:40 | [11 empty] | Downlink SSDR Segment 6 | [5 empty] | Ground Command
1994-04-20 13:17 | 4:45 |  | -20 | 220.7 | 2916.2 | [6 empty] | S20D
1994-04-20 13:30 | 4:58 |  | -27.8 | 220.6 | 2941.7 | [6 empty] | Aposelene