## Sheet1
UTC TIME REFERENCE | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-04-28 10:33 | 0:00 |  | -29.1 | 116.9 | 2979.4 | [6 empty] | Aposelene | [6 empty] | Downlinking SSDR Segment 3 (orbit 323)
1994-04-28 10:35 | 0:02 |  | -30 | 116.9 | 2979 | [6 empty] | S30D
1994-04-28 10:50 | 0:17 | [17 empty] | DSN ERROR: DSN performed an uplink sweep an hour early resulting in some data dropout
1994-04-28 10:52 | 0:19 |  | -40 | 116.9 | 2927.3 | [6 empty] | S40D
1994-04-28 11:08 | 0:35 |  | -50 | 116.9 | 2795.1 | [6 empty] | S50D
Standard Prep1 Script
1994-04-28 11:08 | 0:35 | 0 | [10 empty] | NIR camera & cryocooler ON; SA mode to AUTO
End Prep1 Script
1994-04-28 11:23 | 0:50 |  | -60 | 117 | 2599.2 | [6 empty] | S60D
Standard Prep2 Script
1994-04-28 11:33 | 1:00 | 0 | [10 empty] | Laser heater ON; Open sensor door if closed
End Prep2 Script
1994-04-28 11:37 | 1:04 |  | -70 | 117.4 | 2361.3 | [6 empty] | S70D
#VALUE!
1994-04-28 11:44 | 1:11 | 0 | [10 empty] | Msg "WARNING: Omni/2k in 1 min.."
1994-04-28 11:44 | 1:11 | 25 | [10 empty] | LWIR camera and cryocooler ON
1994-04-28 11:45 | 1:12 | 35 | [10 empty] | SSDR to IDLE; Switch to 2 kbps bypass mode | [5 empty] | Data dump stopped
1994-04-28 11:46 | 1:13 | 60 | [10 empty] | Switch to omni antennas
1994-04-28 11:47 | 1:14 | 60 | [10 empty] | Select ST-B; Set SA step rate to HI; Slew s/c sensors to Crux (ACSMode=StarPointing, Index=3) | [5 empty] | Slew to Crux
1994-04-28 11:49 | 1:16 |  | -80 | 118.8 | 2103.3 | [6 empty] | S80D
1994-04-28 11:52 | 1:19 |  | -83.1 | 120 | 2022.6 | [5 empty] | PMK | LOS
1994-04-28 11:53 | 1:20 | 360 | [10 empty] | Initialize filters (DHU SEQT 27); Load crux exposure table (ldluncrux); Record in SSDR Segment 4 | [5 empty] | Start in SSDR Segment 4
1994-04-28 11:53 | 1:20 | 40 | [10 empty] | Perform NIR imaging (DHU SEQT 31) | [5 empty] | Dark field imaging
1994-04-28 11:54 | 1:20 | 15 | [10 empty] | Stop imaging - select ST-B; Switch to lunar mapping mode (ACSMode=LunarMapping) | [5 empty] | Slew sensors to nadir mapping
1994-04-28 11:55 | 1:22 | 90 | [10 empty] | UV & HR cameras ON
#VALUE!
#VALUE!
1994-04-28 11:59 | 1:25 | 0 | [10 empty] | Initialize filters (DHU SEQT 28); Load exposure table LUNARZ85S; Load exposure table LUNARH85S
1994-04-28 11:59 | 1:26 | 30 | [10 empty] | Switch to lunar mapping mode (ACSMode=LunarMapping); Start Imaging (DHU SEQT 21) | [5 empty] | START MAPPING
1994-04-28 12:00 | 1:26 | 30 | [9 empty] | MAXS | Set SA step rate to LO
1994-04-28 12:00 | 1:26 |  | -89.5 | 205.9 | 1843.8 | [6 empty] | South Pole
1994-04-28 12:00 | 1:27 |  | -89 | 264 | 1822.9 | [6 empty] | LDAWN
1994-04-28 12:09 | 1:36 | 551 | [9 empty] | S80A | Slew to stereo attitude using inertial pointing (GNC12STEREO01); Load exposure table LUNARZ85S; Load exposure table LUNARH85S; Select DHU SEQT 20 | [5 empty] | STEREO MAPPING PHASE A Offset is approx. +27.5° longitude (East) using inertial pointing steps
1994-04-28 12:09 | 1:36 |  | -80 | 292.8 | 1595.6 | [6 empty] | S80A
1994-04-28 12:17 | 1:44 | 479 | -70 | 294.3 | 1366.7 | [6 empty] | S70A | Load exposure table LUNARZ75S; Load exposure table LUNARH75S; Select DHU SEQT 19
1994-04-28 12:20 | 1:47 | 207 | [9 empty] | S65A | Stereo pointing attitude using GNC12STEREO02; Select DHU SEQT 12 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:24 | 1:51 | 207 | [9 empty] | S60A | Stereo pointing attitude using GNC12STEREO03; Load exposure table LUNARZ65S; Load exposure table LUNARH65S | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:24 | 1:51 |  | -60 | 294.7 | 1161.9 | [6 empty] | S60A
1994-04-28 12:27 | 1:54 | 182 | [9 empty] | S55A | Stereo pointing attitude using GNC12STEREO04; Select DHU SEQT 11 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:30 | 1:57 | 182 | [9 empty] | S50A | Stereo pointing attitude using GNC12STEREO05; Load exposure table LUNARZ55S; Load exposure table LUNARH55S; Select DHU SEQT 10 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:30 | 1:57 |  | -50 | 294.9 | 983 | [6 empty] | S50A
1994-04-28 12:30 | 1:57 | 12 | [10 empty] | Laser Power ON
1994-04-28 12:33 | 1:59 | 156 | [9 empty] | S45A | Stereo pointing attitude using GNC12STEREO06; Select DHU SEQT 9 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:35 | 2:02 | 156 | -40 | 295.1 | 829.8 | [6 empty] | S40A | Slew to stereo Phase B attitude using GNC12STEREO07; Load exposure table LUNARZ45S; Load exposure table LUNARH45S | [5 empty] | STEREO MAPPING PHASE B Offset is approx. +13.75° longitude (East) using inertial pointing steps
1994-04-28 12:36 | 2:03 | 60 | [10 empty] | Record in SSDR Segment 5 | [5 empty] | SSDR Segment 5
1994-04-28 12:38 | 2:04 | 84 | [9 empty] | S35A | Stereo pointing attitude using GNC12STEREO08; Select DHU SEQT 8 | [5 empty] | Slew to next stereo attitude (inertial pointing) Start laser ranging (oblique)
1994-04-28 12:40 | 2:07 | 144 | [9 empty] | S30A | Stereo pointing attitude using GNC12STEREO09; Load exposure table LUNARZ35S; Load exposure table LUNARH35S | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:40 | 2:07 |  | -30 | 295.1 | 701.4 | [6 empty] | S30A
1994-04-28 12:42 | 2:09 | 131 | [9 empty] | S25A | Stereo pointing attitude using GNC12STEREO10; Select DHU SEQT 7 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:44 | 2:11 | 131 | [9 empty] | S20A | Stereo pointing attitude using GNC12STEREO11; Load exposure table LUNARZ35S; Load exposure table LUNARH35S | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:44 | 2:11 |  | -20 | 295.2 | 596.3 | [6 empty] | S20A
1994-04-28 12:46 | 2:13 | 121 | [9 empty] | S15A | Stereo pointing attitude using GNC12STEREO12; Select DHU SEQT 6 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:48 | 2:15 | 121 | [9 empty] | S10A | Stereo pointing attitude using GNC12STEREO13 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:48 | 2:15 |  | -10 | 295.3 | 513 | [6 empty] | S10A
1994-04-28 12:50 | 2:17 | 113 | [9 empty] | S05A | Stereo pointing attitude using GNC12STEREO14; Select DHU SEQT 5 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:52 | 2:19 | 113 | [9 empty] | MEQA | Stereo pointing attitude using GNC12STEREO15; Load exposure table LUNARZ35N; Load exposure table LUNARH35N | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:52 | 2:19 |  | 0 | 295.3 | 450.1 | [6 empty] | Equator - A
1994-04-28 12:54 | 2:21 | 109 | [9 empty] | N05A | Stereo pointing attitude using GNC12STEREO16; Select DHU SEQT 0 | [5 empty] | Slew to next stereo attitude (inertial pointing) KEQ_09X.UMI loaded in SEQT 0
1994-04-28 12:56 | 2:23 | 108 | [9 empty] | N10A | Stereo pointing attitude using GNC12STEREO17 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:56 | 2:23 |  | 10 | 295.4 | 406.5 | [6 empty] | N10A
1994-04-28 12:57 | 2:24 | 105 | [9 empty] | N15A | Stereo pointing attitude using GNC12STEREO18 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:59 | 2:26 | 104 | [9 empty] | N20A | Stereo pointing attitude using GNC12STEREO19 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 12:59 | 2:26 |  | 20 | 295.5 | 381.3 | [6 empty] | N20A
1994-04-28 13:01 | 2:28 | 94 | [9 empty] | N25A | Stereo pointing attitude using GNC12STEREO20 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 13:02 | 2:29 |  | 29.1 | 295.5 | 374 | [6 empty] | Periselene
1994-04-28 13:03 | 2:29 | 112 | [9 empty] | N30A | Stereo pointing attitude using GNC12STEREO21 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 13:03 | 2:30 |  | 30 | 295.5 | 374.1 | [6 empty] | N30A
1994-04-28 13:04 | 2:31 | 103 | [9 empty] | N35A | Stereo pointing attitude using GNC12STEREO22 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 13:06 | 2:33 | 103 | [9 empty] | N40A | Stereo pointing attitude using GNC12STEREO23; Load exposure table LUNARZ45N; Load exposure table LUNARH45N | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 13:06 | 2:33 |  | 40 | 295.6 | 384.7 | [6 empty] | N40A
1994-04-28 13:08 | 2:35 | 105 | [9 empty] | N45A | Stereo pointing attitude using GNC12STEREO24 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 13:09 | 2:36 | [11 empty] | Set SA step rate to HI | [5 empty] | Ground Command - battery discharging due to bad sun angle
1994-04-28 13:10 | 2:36 | 106 | [9 empty] | N50A | Stereo pointing attitude using GNC12STEREO25; Load exposure table LUNARZ55N; Load exposure table LUNARH55N | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 13:10 | 2:36 |  | 50 | 295.8 | 413.2 | [6 empty] | N50A
1994-04-28 13:11 | 2:38 | 109 | [9 empty] | N55A | Stereo pointing attitude using GNC12STEREO26; Select DHU SEQT 5 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 13:13 | 2:40 | 109 | [9 empty] | N60A | Stereo pointing attitude using GNC12STEREO27; Load exposure table LUNARZ65N; Load exposure table LUNARH65N | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 13:13 | 2:40 |  | 60 | 296 | 460.4 | [6 empty] | N60A
1994-04-28 13:15 | 2:42 | 115 | [9 empty] | N65A | Stereo pointing attitude using GNC12STEREO28; Select DHU SEQT 6 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-04-28 13:17 | 2:44 | 115 | [9 empty] | N70A | Switch to lunar mapping mode (ACSMode=LunarMapping); Load exposure table LUNARZ85N; Load exposure table LUNARH85N; Select DHU SEQT 7 | [5 empty] | Resume nadir pointing for laser ranging
1994-04-28 13:17 | 2:44 |  | 70 | 296.5 | 527 | [6 empty] | N70A
1994-04-28 13:18 | 2:45 | 60 | [10 empty] | Record in SSDR Segment 6 | [5 empty] | SSDR Segment 6
1994-04-28 13:21 | 2:48 | 186 | [9 empty] | N80A | Load exposure table LUNARZ85N; Load exposure table LUNARH85N; Select DHU SEQT 8
#VALUE!
1994-04-28 13:21 | 2:48 |  | 80 | 298 | 614.4 | [6 empty] | N80A
1994-04-28 13:26 | 2:52 |  | 89.5 | 27 | 723.8 | [6 empty] | North Pole | [6 empty] | No Data - dump not completed
1994-04-28 13:26 | 2:53 |  | 89 | 82.9 | 733.7 | [6 empty] | LDUSK
#VALUE!
1994-04-28 13:27 | 2:53 | 0 | [10 empty] | Stop Imaging - select ST-B; Laser power OFF; Set SA step rate to HI
1994-04-28 13:27 | 2:54 | 5 | [10 empty] | Slew s/c sensors to Vega (NEWVEGAQT) | [5 empty] | Slew to Vega using new quaternion
1994-04-28 13:27 | 2:54 | 30 | [10 empty] | Park opaque filter on HiRes (DHU SEQT 27)
#VALUE! | #VALUE! | 15 | [10 empty] | Select ST-B; Activate waitwhileslew for 310 sec
#VALUE! | #VALUE! | #VALUE! | [10 empty] | Set SA mode to MANUAL; Load Vega exposure tables (LUNVEGA)
1994-04-28 13:30 | 2:57 | 60 | [10 empty] | Perform LWIR imaging (DHU SEQT 25) | [5 empty] | Start calibration imaging No data
#VALUE! | #VALUE! | 12 | [10 empty] | Perform NIR imaging (DHU SEQT 31) | [5 empty] | No Data
#VALUE! | #VALUE! | 6 | [10 empty] | Load exposure table LUNIRDKS1
1994-04-28 13:31 | 2:57 |  | 80 | 112 | 856.4 | [6 empty] | N80D
#VALUE! | #VALUE! | 6 | [10 empty] | Load exposure table LUNIRDKS2
#VALUE! | #VALUE! | 6 | [10 empty] | Perform UV0 imaging (DHU SEQT 29) | [5 empty] | No Data
#VALUE! | #VALUE! | 12 | [10 empty] | Perform HiRes imaging (DHU SEQT 30) | [5 empty] | No Data
#VALUE! | #VALUE! | 30 | [10 empty] | Stop imaging - select ST-B; Set SA mode to AUTO; UV & HR cameras OFF; IR cameras & cryocoolers OFF; Slew s/c HGA to Earth (ACSMode=EarthPointing, Center); Activate waitwhileslew for 360 sec | [5 empty] | Slew HGA to Earth with active waitwhileslew
1994-04-28 13:36 | 3:03 |  | 70 | 113.5 | 1014.4 | [6 empty] | N70D
1994-04-28 13:37 | 3:04 | #VALUE! | [10 empty] | Switch to HGA | [5 empty] | READY FOR DATA DUMP - Time approximate
#VALUE!
1994-04-28 13:38 | 3:05 | [11 empty] | Switch to DHU mode @ 128 kbps | [5 empty] | Ground Command
1994-04-28 13:40 | 3:07 | [11 empty] | Resume downlink SSDR Segment 3 | [5 empty] | Ground Command - orbit 323
1994-04-28 13:42 | 3:09 |  | 60 | 114 | 1198.2 | [6 empty] | N60D
1994-04-28 13:49 | 3:16 |  | 50 | 114.2 | 1407.7 | [6 empty] | N50D
1994-04-28 13:52 | 3:19 | [11 empty] | Read dosimeter latch values | [5 empty] | Ground Command
1994-04-28 13:57 | 3:24 | [11 empty] | Expose dosimeter | [5 empty] | Scheduled Command
1994-04-28 13:58 | 3:24 |  | 40 | 114.3 | 1640.6 | [6 empty] | N40D
1994-04-28 14:02 | 3:29 | [11 empty] | Update state vector (GNC53_28APR1200) | [5 empty] | Ground Command
1994-04-28 14:07 | 3:34 |  | 30 | 114.3 | 1892 | [6 empty] | N30D
1994-04-28 14:18 | 3:45 |  | 20 | 114.4 | 2152.7 | [6 empty] | N20D
1994-04-28 14:30 | 3:57 | [11 empty] | Downlink SSDR Segment 4 | [5 empty] | Ground Command
1994-04-28 14:30 | 3:57 |  | 10 | 114.3 | 2408.4 | [6 empty] | N10D
1994-04-28 14:32 | 3:59 | [11 empty] | Uplink and schedule L325 scripts | [5 empty] | Ground Command
1994-04-28 14:44 | 4:11 |  | 0 | 114.3 | 2640 | [6 empty] | Equator - D
1994-04-28 14:49 | 4:16 |  | -3.2 | 114.3 | 2705.3 | [5 empty] | GDS | LOS
1994-04-28 15:00 | 4:27 |  | -10 | 114.3 | 2825.6 | [6 empty] | S10D
1994-04-28 15:07 | 4:34 | [11 empty] | Downlink SSDR Segment 5 | [5 empty] | Ground Command
1994-04-28 15:16 | 4:43 |  | -20 | 114.2 | 2943.7 | [6 empty] | S20D
1994-04-28 15:32 | 4:58 |  | -29 | 114.2 | 2979.6 | [6 empty] | Aposelene