## Sheet1
UTC TIME REFERENCE | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-05-01 08:11 | 0:00 |  | -28.3 | 78.7 | 2980.9 | [6 empty] | Aposelene | Waiting for start of 338 mapping in 2 kbps bypass mode on omnis | [5 empty] | Note: Orbit 337 mapping activities canceled because of HKP crash/reset that occurred at ~04:15 S/C in inertial pointing mode for thermal conditioning
1994-05-01 08:14 | 0:03 |  | -30 | 78.7 | 2979.6 | [6 empty] | S30D
1994-05-01 08:17 | 0:06 |  | -32 | 78.6 | 2975.4 | [5 empty] | GDS | AOS
1994-05-01 08:31 | 0:20 |  | -40 | 78.6 | 2920.8 | [6 empty] | S40D
Standard Prep1 Script
1994-05-01 08:47 | 0:36 | 0 | [10 empty] | NIR camera & cryocooler ON; Solar Arrays mode to AUTO
End Prep1 Script
1994-05-01 08:47 | 0:36 |  | -50 | 78.7 | 2782.4 | [6 empty] | S50D
1994-05-01 09:02 | 0:51 |  | -60 | 78.8 | 2581.8 | [6 empty] | S60D
Standard Prep2 Script
1994-05-01 09:12 | 1:01 | 0 | [10 empty] | Laser heater ON; Open sensor door if closed
End Prep2 Script
1994-05-01 09:16 | 1:05 |  | -70 | 79.2 | 2341.2 | [6 empty] | S70D
#VALUE!
1994-05-01 09:22 | 1:11 | 0 | [10 empty] | Msg "WARNING: Omni/2k in 1 min.."
1994-05-01 09:23 | 1:12 | 25 | [10 empty] | LWIR camera and cryocooler ON
1994-05-01 09:23 | 1:12 | 35 | [10 empty] | SSDR to IDLE; Switch to 2 kbps bypass mode
1994-05-01 09:24 | 1:13 | 60 | [10 empty] | Switch to omni antennas
1994-05-01 09:25 | 1:14 | 60 | [10 empty] | Select ST-B; Set SA step rate to HI; Slew s/c sensors to Crux (ACSMode=StarPointing, Index=3) | [5 empty] | Slew to Crux
1994-05-01 09:28 | 1:17 |  | -80 | 80.6 | 2081.9 | [6 empty] | S80D
1994-05-01 09:31 | 1:20 | 360 | [10 empty] | Initialize filters (DHU SEQT 27); Load crux exposure table (ldluncrux); Record in SSDR Segment 1 | [5 empty] | Start in SSDR Segment 1
1994-05-01 09:32 | 1:21 | 40 | [10 empty] | Perform NIR imaging (DHU SEQT 31) | [5 empty] | Dark field imaging
1994-05-01 09:32 | 1:21 | 15 | [10 empty] | Stop imaging - select ST-B; Switch to lunar mapping mode (ACSMode=LunarMapping) | [5 empty] | Slew sensors to nadir mapping
1994-05-01 09:34 | 1:23 | 90 | [10 empty] | UV & HR cameras ON
#VALUE!
#VALUE!
1994-05-01 09:37 | 1:26 | 0 | [10 empty] | Initialize filters (DHU SEQT 28); Load exposure table LUNARZ85S; Load exposure table LUNARH85S
1994-05-01 09:38 | 1:27 | 30 | [10 empty] | Switch to lunar mapping mode (ACSMode=LunarMapping); Start Imaging (DHU SEQT 21) | [5 empty] | START MAPPING
1994-05-01 09:38 | 1:27 |  | -89.5 | 167.4 | 1822.7 | [6 empty] | South Pole
1994-05-01 09:39 | 1:28 |  | -89 | 224.7 | 1802.1 | [6 empty] | LDAWN
1994-05-01 09:47 | 1:36 |  | -80 | 254.5 | 1575.5 | [6 empty] | S80A
1994-05-01 09:47 | 1:36 | 575 | [9 empty] | S80A | Slew to stereo attitude using inertial pointing (GNC12STEREO01); Load exposure table LUNARZ85S; Load exposure table LUNARH85S; Select DHU SEQT 20 | [5 empty] | STEREO MAPPING PHASE A Offset is approx. +27.5° longitude (East) using inertial pointing steps
1994-05-01 09:55 | 1:44 | 472 | -70 | 256 | 1348.2 | [6 empty] | S70A | Set SA step rate to LO; Load exposure table LUNARZ75S; Load exposure table LUNARH75S; Select DHU SEQT 19
1994-05-01 09:56 | 1:45 |  | -68.8 | 256.1 | 1321.4 | [5 empty] | MAD | LOS
1994-05-01 09:58 | 1:48 | 205.5 | [9 empty] | S65A | Stereo pointing attitude using GNC12STEREO02; Select DHU SEQT 12 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:02 | 1:51 | 205.5 | [9 empty] | S60A | Stereo pointing attitude using GNC12STEREO03; Load exposure table LUNARZ65S; Load exposure table LUNARH65S | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:02 | 1:51 |  | -60 | 256.5 | 1145.3 | [6 empty] | S60A
1994-05-01 10:05 | 1:54 | 180 | [9 empty] | S55A | Stereo pointing attitude using GNC12STEREO04; Select DHU SEQT 11 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:06 | 1:55 | 43 | [10 empty] | Laser Power ON
1994-05-01 10:08 | 1:57 | 137 | [9 empty] | S50A | Stereo pointing attitude using GNC12STEREO05; Load exposure table LUNARZ55S; Select DHU SEQT 10 | [5 empty] | Slew to next stereo attitude (inertial pointing) Stop HiRes imaging
1994-05-01 10:08 | 1:57 |  | -50 | 256.7 | 968.4 | [6 empty] | S50A
1994-05-01 10:10 | 2:00 | 160 | [9 empty] | S45A | Stereo pointing attitude using GNC12STEREO06; Select DHU SEQT 9 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:13 | 2:02 | 160 | -40 | 256.8 | 817.2 | [6 empty] | S40A | Slew to stereo Phase B attitude using GNC12STEREO07; Load exposure table LUNARZ45S | [5 empty] | STEREO MAPPING PHASE B Offset is approx. +13.75° longitude (East) using inertial pointing steps
1994-05-01 10:14 | 2:03 | 60 | [10 empty] | Record in SSDR Segment 2 | [5 empty] | SSDR Segment 2
1994-05-01 10:16 | 2:05 | 83 | [9 empty] | S35A | Stereo pointing attitude using GNC12STEREO08; Select DHU SEQT 8 | [5 empty] | Slew to next stereo attitude (inertial pointing) Start laser ranging (oblique)
1994-05-01 10:18 | 2:07 | 143 | -30 | 256.9 | 690.7 | [6 empty] | S30A | Stereo pointing attitude using GNC12STEREO09; Load exposure table LUNARZ35S | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:20 | 2:09 | 130 | [9 empty] | S25A | Switch to offset lunar mapping mode using GNC14STEREO (ACSMode=LunarMapping, CenterAngle=-0.23); Select DHU SEQT 7 | [5 empty] | STEREO MAPPING PHASE C Switch to offset mapping mode with offset angle of 13.18° to East
1994-05-01 10:22 | 2:12 | 130 | [9 empty] | S20A | Load exposure table LUNARZ35S
1994-05-01 10:22 | 2:12 |  | -20 | 257 | 587.4 | [6 empty] | S20A
1994-05-01 10:24 | 2:14 | 120.5 | [10 empty] | Select DHU SEQT 6
1994-05-01 10:26 | 2:16 |  | -10 | 257 | 505.8 | [6 empty] | S10A
1994-05-01 10:28 | 2:17 | 233.5 | [10 empty] | Select DHU SEQT 5
1994-05-01 10:30 | 2:19 | 113 | 0 | 257.1 | 444.5 | [6 empty] | Equator - A | Load exposure table LUNARZ35N
1994-05-01 10:32 | 2:21 | 107.5 | [10 empty] | Select DHU SEQT 0 | [5 empty] | KEQ_09X.UMI loaded in SEQT 0
1994-05-01 10:34 | 2:23 |  | 10 | 257.2 | 402.4 | [6 empty] | N10A
1994-05-01 10:34 | 2:23 | [11 empty] | IMU B OFF | [5 empty] | Ground Command
1994-05-01 10:37 | 2:26 |  | 20 | 257.2 | 378.6 | [6 empty] | N20A
1994-05-01 10:39 | 2:28 | 401.5 | [9 empty] | N25A | Stereo pointing attitude using GNC12STEREO20 | [5 empty] | STEREO OBSERVATION PHASE D Return to inertial pointing for stereo observation
1994-05-01 10:40 | 2:29 |  | 28.3 | 257.3 | 372.6 | [6 empty] | Periselene
1994-05-01 10:41 | 2:30 | 121 | 30 | 257.3 | 372.8 | [6 empty] | N30A | Stereo pointing attitude using GNC12STEREO21 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:42 | 2:32 | 103 | [9 empty] | N35A | Stereo pointing attitude using GNC12STEREO22 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:44 | 2:33 | 103 | [9 empty] | N40A | Stereo pointing attitude using GNC12STEREO23; Load exposure table LUNARZ45N | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:44 | 2:33 |  | 40 | 257.4 | 384.8 | [6 empty] | N40A
1994-05-01 10:46 | 2:35 | 105.5 | [9 empty] | N45A | Stereo pointing attitude using GNC12STEREO24 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:47 | 2:36 | [11 empty] | SA-A mode to MANUAL; Rotate SA-A towards sun | [5 empty] | Ground Command - bad sun angle, battery discharging
1994-05-01 10:47 | 2:37 | 105.5 | 50 | 257.6 | 414.9 | [6 empty] | N50A | Stereo pointing attitude using GNC12STEREO25; Load exposure table LUNARZ55N; Load exposure table LUNARH55N | [5 empty] | Slew to next stereo attitude (inertial pointing) Resume HiRes imaging
1994-05-01 10:49 | 2:39 | 109 | [9 empty] | N55A | Stereo pointing attitude using GNC12STEREO26; Select DHU SEQT 5 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:51 | 2:40 | 109 | [9 empty] | N60A | Stereo pointing attitude using GNC12STEREO27; Load exposure table LUNARZ65N; Load exposure table LUNARH65N | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:51 | 2:40 |  | 60 | 257.8 | 463.6 | [6 empty] | N60A
1994-05-01 10:53 | 2:42 | [11 empty] | SA-A mode to AUTO | [5 empty] | Ground Command
1994-05-01 10:53 | 2:42 | 115.5 | [9 empty] | N65A | Stereo pointing attitude using GNC12STEREO28; Select DHU SEQT 6 | [5 empty] | Slew to next stereo attitude (inertial pointing)
1994-05-01 10:54 | 2:43 | [11 empty] | SA-B mode to MANUAL; Rotate SA-B towards sun | [5 empty] | Ground Command - bad sun angle, battery still discharging
1994-05-01 10:55 | 2:44 | 115.5 | 70 | 258.3 | 531.9 | [6 empty] | N70A | Switch to lunar mapping mode (ACSMode=LunarMapping); Load exposure table LUNARZ85N; Load exposure table LUNARH85N; Select DHU SEQT 7 | [5 empty] | END STEREO OBSERVATION Resume nadir pointing for laser ranging
1994-05-01 10:56 | 2:45 | 60 | [10 empty] | Record in SSDR Segment 3 | [5 empty] | SSDR Segment 3
1994-05-01 10:59 | 2:48 | 187 | [9 empty] | N80A | Load exposure table LUNARZ85N; Load exposure table LUNARH85N; Select DHU SEQT 8
#VALUE!
1994-05-01 10:59 | 2:48 |  | 80 | 259.8 | 621 | [6 empty] | N80A
1994-05-01 11:01 | 2:50 | [11 empty] | SA-B mode to AUTO | [5 empty] | Ground Command
1994-05-01 11:04 | 2:53 |  | 89.5 | 347.8 | 732.3 | [6 empty] | North Pole
1994-05-01 11:04 | 2:53 |  | 89 | 44 | 742.1 | [6 empty] | LDUSK
#VALUE!
1994-05-01 11:05 | 2:54 | 0 | [10 empty] | Stop Imaging - select ST-B; Laser power OFF; Set SA step rate to HI
1994-05-01 11:05 | 2:54 | 5 | [10 empty] | Slew s/c sensors to Vega (NEWVEGAQT) | [5 empty] | Slew to Vega using new quaternion
1994-05-01 11:05 | 2:54 | 30 | [10 empty] | Park opaque filter on HiRes (DHU SEQT 27)
#VALUE! | #VALUE! | 15 | [10 empty] | Select ST-B; Activate waitwhileslew for 310 sec
1994-05-01 11:06 | 2:55 | [11 empty] | IMU B ON | [5 empty] | Ground Command
1994-05-01 11:08 | 2:58 |  | 80 | 73.8 | 867 | [6 empty] | N80D
#VALUE! | #VALUE! | #VALUE! | [10 empty] | Set SA mode to MANUAL; Load Vega exposure tables (LUNVEGA)
1994-05-01 11:10 | 2:59 | 60 | [10 empty] | Perform LWIR imaging (DHU SEQT 25) | [5 empty] | Start calibration imaging
#VALUE! | #VALUE! | 12 | [10 empty] | Perform NIR imaging (DHU SEQT 31)
#VALUE! | #VALUE! | 6 | [10 empty] | Load exposure table LUNIRDKS1
#VALUE! | #VALUE! | 6 | [10 empty] | Load exposure table LUNIRDKS2
#VALUE! | #VALUE! | 6 | [10 empty] | Perform UV0 imaging (DHU SEQT 29)
#VALUE! | #VALUE! | 12 | [10 empty] | Perform HiRes imaging (DHU SEQT 30)
#VALUE! | #VALUE! | 30 | [10 empty] | Stop imaging - select ST-B; Set SA mode to AUTO; UV & HR cameras OFF; IR cameras & cryocoolers OFF; Slew s/c HGA to Earth (ACSMode=EarthPointing, Center); Activate waitwhileslew for 360 sec | [5 empty] | Slew HGA to Earth with active waitwhileslew
1994-05-01 11:14 | 3:03 |  | 70 | 75.3 | 1027.2 | [6 empty] | N70D
1994-05-01 11:17 | 3:06 | 178 | [10 empty] | Switch to HGA | [5 empty] | READY FOR DATA DUMP - Time approximate
#VALUE!
1994-05-01 11:18 | 3:07 | [11 empty] | Switch to DHU mode @ 128 kbps | [5 empty] | Ground Command
1994-05-01 11:19 | 3:08 | [11 empty] | Downlink SSDR Segment 1 | [5 empty] | Ground Command
1994-05-01 11:20 | 3:09 | [11 empty] | Uplink and schedule L339 scripts | [5 empty] | Ground Command
1994-05-01 11:20 | 3:10 |  | 60 | 75.7 | 1213.2 | [6 empty] | N60D
1994-05-01 11:24 | 3:13 | [11 empty] | Slew s/c around X axis to cool battery | [5 empty] | Ground Command - inertial ptg
1994-05-01 11:27 | 3:17 |  | 50 | 76 | 1424.9 | [6 empty] | N50D
1994-05-01 11:36 | 3:25 |  | 40 | 76.1 | 1659.9 | [6 empty] | N40D
1994-05-01 11:37 | 3:26 | [11 empty] | IMU B OFF | [5 empty] | Ground Command
1994-05-01 11:38 | 3:27 | [11 empty] | Slew s/c around X axis | [5 empty] | Ground Command ST-B blocked by Moon
1994-05-01 11:44 | 3:33 | [11 empty] | Downlink SSDR Segment 2 | [5 empty] | Ground Command
1994-05-01 11:44 | 3:34 | [11 empty] | SA-B mode to MANUAL; Rotate SA-B towards sun | [5 empty] | Ground Command
1994-05-01 11:45 | 3:35 |  | 30 | 76.1 | 1912.7 | [6 empty] | N30D
1994-05-01 11:50 | 3:39 | [11 empty] | SA-B mode to AUTO | [5 empty] | Ground Command
1994-05-01 11:56 | 3:46 |  | 20 | 76.1 | 2173.9 | [6 empty] | N20D
1994-05-01 11:59 | 3:48 | [11 empty] | Slew s/c around X axis to cool battery | [5 empty] | Ground Command - inertial ptg
1994-05-01 12:09 | 3:58 |  | 10 | 76.1 | 2428.8 | [6 empty] | N10D
1994-05-01 12:23 | 4:12 |  | 0 | 76.1 | 2658 | [6 empty] | Equator - D
1994-05-01 12:39 | 4:28 |  | -10 | 76 | 2839.2 | [6 empty] | S10D
1994-05-01 12:55 | 4:44 |  | -20 | 76 | 2951.3 | [6 empty] | S20D
1994-05-01 13:09 | 4:58 | [11 empty] | Downlink SSDR Segment 3 | [5 empty] | Ground Command
1994-05-01 13:09 | 4:58 |  | -28.2 | 75.9 | 2981.1 | [6 empty] | Aposelene