## Sheet1
UTC Time | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-02-19 12:52 | 0:00 | 0 | [10 empty] | BEGIN LOI1 BURN @ 12:51:32 | [5 empty] | S/C in burn maneuver state: • all sensor doors closed • cameras off • omni antenna active • in burn attitude
1994-02-19 12:58 | 0:00 | 370 |  |  | 395 | [7 empty] | END LOI1 BURN | [5 empty] | Duration = 370.12 sec deltaV=460.3 m/s (+0.2% error) BEGIN ORBIT OPERATIONS
1994-02-19 13:05 | 0:07 | [10 empty] | Equator - A | [6 empty] | START REV #1
1994-02-19 13:08 | 0:11 |  | 10 | 107.9 | 539.8 | [6 empty] | N10A
1994-02-19 13:12 | 0:15 |  | 20 | 107.9 | 637.7 | [6 empty] | N20A
1994-02-19 13:14 | 0:17 | [9 empty] | CAN | LOS
1994-02-19 13:17 | 0:19 |  | 30 | 108 | 766.5 | [6 empty] | N30A
1994-02-19 13:21 | 0:24 |  | 40 | 108.1 | 930.7 | [6 empty] | N40A
1994-02-19 13:27 | 0:29 |  | 50 | 108.2 | 1135.6 | [6 empty] | N50A
1994-02-19 13:32 | 0:34 | [11 empty] | ST-A door OPEN | [5 empty] | Ground Command
1994-02-19 13:34 | 0:36 |  | 60 | 108.4 | 1387.9 | [6 empty] | N60A
1994-02-19 13:34 | 0:36 | [11 empty] | Select ST-A | [5 empty] | Ground Command
1994-02-19 13:41 | 0:44 |  | 70 | 108.9 | 1694.5 | [6 empty] | N70A
1994-02-19 14:02 | 1:05 |  | 89.5 | 197.1 | 2496.2 | [6 empty] | North Pole
1994-02-19 14:04 | 1:07 |  | 88.4 | 268.4 | 2568.2 | [6 empty] | LDUSK
1994-02-19 14:17 | 1:19 |  | 80 | 284.2 | 2995.2 | [6 empty] | N80D
1994-02-19 14:17 | 1:19 | [11 empty] | Read dosimeter latch values | [5 empty] | Ground Command
1994-02-19 14:22 | 1:24 | [11 empty] | Expose dosimeter | [5 empty] | Ground Command
1994-02-19 14:35 | 1:37 |  | 70 | 285.6 | 3549.3 | [6 empty] | N70D
1994-02-19 14:58 | 2:00 |  | 60 | 285.9 | 4127.7 | [6 empty] | N60D
1994-02-19 15:25 | 2:27 |  | 50 | 285.9 | 4677.1 | [6 empty] | N50D
1994-02-19 15:57 | 2:59 |  | 40 | 285.8 | 5122.1 | [6 empty] | N40D
1994-02-19 16:12 | 3:14 | [11 empty] | Switch to lunar mapping mode (ACSMode=LunarMapping) | [5 empty] | Ground Command
1994-02-19 16:33 | 3:35 |  | 30 | 285.6 | 5381.6 | [6 empty] | N30D
1994-02-19 16:54 | 0:00 |  | 24.3 | 285.5 | 5423.2 | [6 empty] | Aposelene | [6 empty] | START OF ORBIT 1/2
1994-02-19 16:57 | 0:03 | [11 empty] | Start and initialize SIP | [5 empty] | Ground Command
1994-02-19 17:10 | 0:16 |  | 20 | 285.4 | 5399.7 | [6 empty] | N20D
1994-02-19 17:16 | 0:22 |  | 18.2 | 285.3 | 5376.1 | [5 empty] | PMK | AOS
1994-02-19 17:45 | 0:52 |  | 10 | 285.2 | 5172.3 | [6 empty] | N10D
1994-02-19 17:50 | 0:56 | [11 empty] | SA-B mode to MANUAL; Rotate SA-B away from sun | [5 empty] | Ground Command Battery at full pressure
1994-02-19 18:05 | 1:11 | [11 empty] | Deselect ST; Uplink A- and S-series DHU sequence tables | [5 empty] | Ground Command SEQ and AEQ sequence tables uploaded
1994-02-19 18:18 | 1:24 |  | 0 | 285 | 4749.2 | [6 empty] | Equator - D
1994-02-19 18:27 | 1:33 | [11 empty] | Select ST-A; SA-A mode to AUTO | [5 empty] | Ground Command
1994-02-19 18:46 | 1:52 |  | -10 | 284.8 | 4209.9 | [6 empty] | S10D
1994-02-19 19:07 | 2:13 | [11 empty] | Switch to DHU mode @ 8 kbps; Switch to DHU mode @ 64 kbps | [5 empty] | Ground Command
1994-02-19 19:09 | 2:16 |  | -20 | 284.7 | 3632.1 | [6 empty] | S20D
1994-02-19 19:18 | 2:24 | [11 empty] | Uplink and schedule L001 scripts | [5 empty] | Ground Command
1994-02-19 19:24 | 2:30 | [11 empty] | Upload SEQ_262.UMI in SEQT 26 | [5 empty] | Ground Command
1994-02-19 19:28 | 2:34 |  | -30 | 284.6 | 3072.6 | [6 empty] | S30D
#VALUE!
1994-02-19 19:38 | 2:44 | 0 | [10 empty] | IR cameras & cryocoolers ON; Set SA mode to AUTO
#VALUE!
1994-02-19 19:43 | 2:49 |  | -40 | 284.7 | 2564.3 | [6 empty] | S40D
1994-02-19 19:55 | 3:01 |  | -50 | 284.8 | 2120.6 | [6 empty] | S50D
1994-02-19 20:00 | 3:06 | [11 empty] | Ranging A OFF | [5 empty] | Ground Command
1994-02-19 20:05 | 3:11 |  | -60 | 285 | 1743.5 | [6 empty] | S60D
#VALUE!
1994-02-19 20:09 | 3:15 | 0 | [10 empty] | Deactivate ST; Slew s/c sensors to SGP (ACSMode=StarPointing, Index=1) | [5 empty] | Slew to South Galactic Pole
1994-02-19 20:13 | 3:19 |  | -70 | 285.5 | 1428.5 | [6 empty] | S70D
1994-02-19 20:14 | 3:20 | 300 | [10 empty] | Select ST-A; Sensor door OPEN; UV & HR cameras ON
1994-02-19 20:15 | 3:21 | [11 empty] | Downlink UV1 R/T (Filter=1) image | [5 empty] | Ground Command - data missing
1994-02-19 20:17 | 3:23 | [11 empty] | Switch downlink rate to 8 kbps | [5 empty] | Ground Command
1994-02-19 20:19 | 3:26 |  | -80 | 287.1 | 1168.8 | [6 empty] | S80D
1994-02-19 20:23 | 3:29 | 565 | [10 empty] | Initialize filters (DHU SEQT 26); Record in SSDR Segment 1 | [5 empty] | Start recorder in Segment 1
1994-02-19 20:24 | 3:30 | 35 | [10 empty] | Perform LWIR imaging (DHU SEQT 25) | [5 empty] | Dark field imaging
1994-02-19 20:24 | 3:31 | 30 | [10 empty] | Perform NIR imaging (DHU SEQT 31)
1994-02-19 20:25 | 3:31 | 30 | [10 empty] | Stop imaging - select ST-A
1994-02-19 20:25 | 3:31 | 10 | [10 empty] | Deselect ST; Switch to lunar mapping mode (ACSMode=LunarMapping) | [5 empty] | Slew sensors to nadir
1994-02-19 20:25 | 3:31 |  | -89.4 | 15.4 | 957.6 | [6 empty] | South Pole
1994-02-19 20:26 | 3:32 |  | -88.4 | 82.6 | 930.2 | [6 empty] | LDAWN
1994-02-19 20:30 | 3:36 |  | -80 | 100.5 | 788.5 | [6 empty] | S80A
1994-02-19 20:31 | 3:37 | 350 | [10 empty] | Select ST-A
1994-02-19 20:31 | 3:37 | 10 | [10 empty] | Initialize filters (DHU SEQT 26); Load exposure tables (ldExpTable); Perform lunar imaging (Execute subscript LunarImaging) | [5 empty] | All cameras & filters Data Compression Target 1: South Pole region
1994-02-19 20:31 | 3:38 | 32 | [10 empty] | Stop imaging - select ST-A | [5 empty] | Occurs inside LunarImaging
1994-02-19 20:32 | 3:38 | [11 empty] | Downlink UV1 R/T (Filter=1) image | [5 empty] | Ground Command - data missing
1994-02-19 20:34 | 3:41 |  | -70 | 102.1 | 654.8 | [6 empty] | S70A
1994-02-19 20:35 | 3:42 |  | -67.4 | 102.3 | 626.1 | [5 empty] | GDS | AOS
1994-02-19 20:36 | 3:42 | 263 | [9 empty] | S80A | Load exposure tables (ldExpTable); Perform lunar uncompressed imaging (LunarImaging) | [5 empty] | WAIT includes previous 32 sec. Data missing
1994-02-19 20:36 | 3:43 | 32 | [10 empty] | Stop imaging - select ST-A | [5 empty] | Occurs inside LunarImaging
1994-02-19 20:38 | 3:45 |  | -60 | 102.7 | 552.7 | [6 empty] | S60A
1994-02-19 20:38 | 3:45 | [11 empty] | Switch data rate to 2 kbps | [5 empty] | Ground Command
1994-02-19 20:40 | 3:46 | 230 | [9 empty] | S70A | Record in SSDR Segment 2 | [5 empty] | WAIT includes previous 32 sec. SSDR Segment 2
1994-02-19 20:41 | 3:47 | 47.4 | [10 empty] | Load exposure tables (ldExpTable); Perform lunar imaging (Execute subscript LunarImaging) | [5 empty] | Data missing
1994-02-19 20:41 | [12 empty] | DHU CRASH
1994-02-19 20:42 | 3:48 |  | -50 | 103 | 478.6 | [6 empty] | S50A
1994-02-19 20:43 | [12 empty] | Abort L001 script; Cancel L001 Post script | [5 empty] | Ground Command SCRIPT ABORTED
#VALUE!
1994-02-19 20:46 | 3:52 |  | -40 | 103.1 | 430.1 | [6 empty] | S40A
1994-02-19 20:46 | [12 empty] | SSDR to IDLE | [5 empty] | Ground Command
1994-02-19 20:49 | 3:55 |  | -30 | 103.2 | 405.5 | [6 empty] | S30A
1994-02-19 20:49 | [12 empty] | Switch to DHU bypass mode | [5 empty] | Ground Command
1994-02-19 20:51 | 3:57 |  | -24.3 | 103.3 | 401.8 | [6 empty] | Periselene
1994-02-19 20:52 | [12 empty] | Reset DHU; Uplink DHU version 241; Reinitialize DHU | [5 empty] | Ground Command
1994-02-19 20:52 | 3:59 |  | -20 | 103.3 | 403.9 | [6 empty] | S20A
1994-02-19 20:56 | 4:02 |  | -10 | 103.4 | 425.4 | [6 empty] | S10A
1994-02-19 20:56 | [12 empty] | NIR camera & cryocooler OFF | [5 empty] | Ground Command
1994-02-19 20:59 | 4:05 |  | 0 | 103.5 | 470.5 | [6 empty] | Equator - A
1994-02-19 21:00 | [12 empty] | Uplink ST sequence tables; Cycle ST; Deselect ST; Uplink A- and S-series DHU sequence tables | [5 empty] | Ground Command
1994-02-19 21:03 | 4:09 |  | 10 | 103.5 | 540.9 | [6 empty] | N10A
1994-02-19 21:07 | 4:13 |  | 20 | 103.6 | 638.9 | [6 empty] | N20A
1994-02-19 21:07 | 4:13 | [11 empty] | NIR camera & cryocooler ON | [5 empty] | Ground Command
1994-02-19 21:11 | 4:17 |  | 30 | 103.7 | 768 | [6 empty] | N30A
1994-02-19 21:11 | 4:17 | [11 empty] | Uplink DHU compression tables | [5 empty] | Ground Command
1994-02-19 21:13 | 4:19 | [11 empty] | Upload SEQ_262.UMI in SEQT 26 | [5 empty] | Ground Command
1994-02-19 21:16 | 4:22 |  | 40 | 103.8 | 932.4 | [6 empty] | N40A
1994-02-19 21:21 | 4:27 | [11 empty] | Uplink exposure tables | [5 empty] | Ground Command
1994-02-19 21:21 | 4:28 |  | 50 | 104 | 1137.6 | [6 empty] | N50A
1994-02-19 21:24 | 4:30 | [11 empty] | Select ST-A | [5 empty] | Ground Command
1994-02-19 21:24 | 4:31 | [11 empty] | Select DHU SEQT 0 | [5 empty] | Ground Command Un/compressed images incl. ST
1994-02-19 21:25 | 4:31 | [11 empty] | Stop imaging - select ST-A | [5 empty] | Ground Command
1994-02-19 21:26 | 4:32 | [11 empty] | Select DHU SEQT 0 | [5 empty] | Ground Command Un/compressed images incl. ST
1994-02-19 21:26 | 4:32 | [11 empty] | Stop imaging - select ST-A | [5 empty] | Ground Command
1994-02-19 21:26 | 4:33 | [11 empty] | Initialize filters (DHU SEQT 26) | [5 empty] | Ground Command
1994-02-19 21:26 | 4:33 | [11 empty] | Select ST-A | [5 empty] | Ground Command
1994-02-19 21:27 | 4:33 | [11 empty] | Select DHU SEQT 0 | [5 empty] | Ground Command Un/compressed images incl. ST
1994-02-19 21:27 | 4:33 | [11 empty] | Stop imaging - select ST-A | [5 empty] | Ground Command
1994-02-19 21:27 | 4:34 | [11 empty] | Record in SSDR Segment 3 | [5 empty] | Ground Command SSDR Segment 3
1994-02-19 21:28 | 4:34 |  | 60 | 104.2 | 1390.1 | [6 empty] | N60A
1994-02-19 21:28 | 4:35 | [11 empty] | Select DHU SEQT 0 | [5 empty] | Ground Command Data Compression Target 19: Compton crater (Lat. 53° to 60°)
1994-02-19 21:29 | 4:35 | [11 empty] | Stop imaging - select ST-A | [5 empty] | Ground Command
1994-02-19 21:29 | 4:35 | [11 empty] | Switch data rate to 8 kbps; Switch to DHU mode | [5 empty] | Ground Command
1994-02-19 21:31 | 4:37 | [11 empty] | Dump UV1 R/T image (filter=4) | [5 empty] | Ground Command - data missing
1994-02-19 21:31 | 4:38 | [11 empty] | Select DHU SEQT 0 | [5 empty] | Ground Command Un/compressed images incl. ST
1994-02-19 21:32 | 4:39 | [11 empty] | Stop imaging - select ST-A | [5 empty] | Ground Command
1994-02-19 21:34 | 4:40 | [11 empty] | Select DHU SEQT 0 | [5 empty] | Ground Command Un/compressed images incl. ST
1994-02-19 21:34 | 4:40 | [11 empty] | Stop imaging - select ST-A | [5 empty] | Ground Command
1994-02-19 21:36 | 4:42 |  | 70 | 104.7 | 1697.1 | [6 empty] | N70A
1994-02-19 21:36 | 4:42 | [11 empty] | Select DHU SEQT 0 | [5 empty] | Ground Command Un/compressed images incl. ST
1994-02-19 21:36 | 4:42 | [11 empty] | Dump UV1 R/T image (filter=1) | [5 empty] | Ground Command - data missing
1994-02-19 21:37 | 4:43 | [11 empty] | Stop imaging - select ST-A | [5 empty] | Ground Command
1994-02-19 21:40 | 4:46 | [11 empty] | Select DHU SEQT 0 | [5 empty] | Ground Command Un/compressed images incl. ST
1994-02-19 21:40 | 4:46 | [11 empty] | Dump NIR R/T image (filter=6) | [5 empty] | Ground Command - data missing
1994-02-19 21:41 | [12 empty] | DHU CRASH
1994-02-19 21:41 | 4:47 | [11 empty] | Stop imaging - select ST-A | [5 empty] | Ground Command - failed
1994-02-19 21:43 | [12 empty] | Switch to DHU bypass mode | [5 empty] | Ground Command
1994-02-19 21:44 | 4:50 | [11 empty] | Switch data rate to 2 kbps | [5 empty] | Ground Command
1994-02-19 21:45 | 4:51 |  | 80 | 106.3 | 2065.8 | [6 empty] | N80A
1994-02-19 21:47 | [12 empty] | NIR cryocooler OFF | [5 empty] | Ground Command
1994-02-19 21:48 | [12 empty] | All cameras (except ST) OFF | [5 empty] | Ground Command
1994-02-19 21:51 | [12 empty] | Reset DHU; Uplink DHU version 241; Reinitialize DHU | [5 empty] | Ground Command
1994-02-19 21:57 | 5:03 |  | 89.4 | 192.7 | 2499.4 | [6 empty] | North Pole
1994-02-19 21:59 | 5:05 |  | 88.4 | 261.6 | 2569.6 | [6 empty] | LDUSK
1994-02-19 21:59 | [12 empty] | Uplink ST sequence tables; Select ST-A | [5 empty] | Ground Command
1994-02-19 22:02 | 5:08 | [11 empty] | Deselect ST; Slew HGA to Goldstone (ACSMode=EarthPointing, GDS) | [5 empty] | Ground Command
1994-02-19 22:08 | 5:14 | [11 empty] | Select ST-A | [5 empty] | Ground Command
1994-02-19 22:10 | 5:16 | [11 empty] | ST-B door OPEN | [5 empty] | Ground Command Not getting matches with ST-A
1994-02-19 22:11 | 5:18 |  | 80 | 279.5 | 2998.6 | [6 empty] | N80D
1994-02-19 22:12 | 5:18 | [11 empty] | Select ST-B | [5 empty] | Ground Command
1994-02-19 22:13 | 5:19 | [11 empty] | Switch to HGA | [5 empty] | Ground Command
1994-02-19 22:17 | 5:23 | [11 empty] | Switch to DHU mode @ 128 kbps | [5 empty] | Ground Command
1994-02-19 22:19 | 5:25 | [11 empty] | Downlink SSDR Segment 3 | [5 empty] | Ground Command
1994-02-19 22:29 | 5:36 |  | 70 | 281.1 | 3552.8 | [6 empty] | N70D
1994-02-19 22:30 | 5:36 | [11 empty] | Downlink SSDR Segment 1 | [5 empty] | Ground Command
1994-02-19 22:52 | 5:58 |  | 60 | 281.4 | 4131.1 | [6 empty] | N60D
1994-02-19 23:19 | 6:26 |  | 50 | 281.5 | 4680 | [6 empty] | N50D
1994-02-19 23:38 | 6:44 | [11 empty] | Downlink SSDR Segment 2 | [5 empty] | Ground Command
1994-02-19 23:51 | 6:58 |  | 40 | 281.4 | 5123.9 | [6 empty] | N40D
1994-02-19 23:57 | 7:03 | [11 empty] | SSDR to IDLE - downlink complete | [5 empty] | Ground Command
1994-02-20 00:27 | 7:33 |  | 30 | 281.2 | 5382 | [6 empty] | N30D
1994-02-20 00:48 | 7:54 |  | 24.3 | 281.1 | 5422.6 | [6 empty] | Aposelene
LunarImaging Subscript
|  | 0 | [10 empty] | Disable IPE processing (autoexp off); Load compression parameters; Start imaging (DHU SEQT 0) | [5 empty] | AEQ_33.UMI loaded in SEQT 0 Both compressed & uncomp. images for all cameras incl. ST
|  | 14 | [10 empty] | Enable Autoexposure | [5 empty] | For UV1,HR,NIR & LWIR
|  | 14 | [10 empty] | Stop imaging - select ST-A
|  | 4 | [10 empty] | Disable IPE processing (autoexp off) | [5 empty] | End Subscript