## Sheet1
UTC Time | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
BEGIN DARKFIELD TEST
1994-02-16 00:14 | [12 empty] | TURN ON LWIR, NIR CAMERAS | [5 empty] | NOTE: THIS TEST EXECUTED PROPERLY BUT THE IMAGES WERE NOT SAVED TO THE SSDR
1994-02-16 00:17 | [12 empty] | CLOSE Startracker Doors
1994-02-16 00:23 | [12 empty] | Record in SSDR Segment 2
1994-02-16 00:31 | [12 empty] | Execute STDark (Perform Startracker Dark fields)
Load up new STA Exposure Settings every 6 seconds (18 sets in all)
[13 empty] | Take Startracker A Dark fields (DHUSEL13) | [5 empty] | Uncompressed STA Images No Data
Load up new STB Exposure Settings every 6 seconds (18 sets in all)
[13 empty] | Take Startracker B Darkfields (DHUSEL14) | [5 empty] | Uncompressed STB Images No Data
1994-02-16 00:36 | [12 empty] | Open STA Door
1994-02-16 00:36 | [12 empty] | Activate STA (DHUSEL1)
Turn ON Hires, UV/VIS Cameras
1994-02-16 00:36 | [12 empty] | Initialize Filters; DHUSEL26
1994-02-16 00:36 | [12 empty] | DHUSELNO
1994-02-16 00:41 | [12 empty] | Start UV/Vis Darkfields
Upload new UVV Exposure settings every 2 seconds (18 sets in all)
[13 empty] | Take Darkfield Images (DHUSEL15) | [5 empty] | No Data
DHUSEL1
Turn OFF UV/Vis Camera
Start Hires Darkfields
Upload new Hires Exposure settings every 2 seconds (27 sets in all)
[13 empty] | Take Darkfield Images (DHUSEL16) | [5 empty] | No Data
DHUSEL1
Turn OFF Hires Camera
1994-02-16 00:58 | [12 empty] | Slew S/C so Sensors Point to South Galatic Pole; (GNC12SPG01)
1994-02-16 00:58 | [10 empty] | MAD | LOS
1994-02-16 01:05 | [12 empty] | Open Sensor Door
1994-02-16 01:09 | [12 empty] | Start NIR Darkfields
Upload new NIR Exposure settings every second (20 sets in all)
[13 empty] | Take NIR Darkfield Images (DHUSEL18) | [5 empty] | No Data
DHUSELNO
Turn OFF NIR Camera
Start LWIR Darkfields
Upload new LWIR Exposure settings every second (20 sets in all)
[13 empty] | Take LWIR Darkfield images (DHUSEL17) | [5 empty] | No Data
DHUSEL 1
Turn OFF LWIR Camera
Close Sensor Door
Slew S/C to Sun-Soaked Attitude (GNC12SUNRW)
END DARKFIELD TEST
Begin Cooldown Test
1994-02-15 02:15 | [12 empty] | Slew S/C to point Sensors to South Galatic Pole (GNC12SGP01)
1994-02-16 02:21 | [12 empty] | OPEN SENSOR DOOR
1994-02-16 02:32 | [12 empty] | Open Startracker B Door
1994-02-16 02:36 | [12 empty] | DHUSEL21
1994-02-16 02:37 | [12 empty] | Activate Startracker B (DHUSEL2)
1994-02-16 02:50 | [12 empty] | Turn ON NIR, LWIR Cameras
1994-02-16 02:50 | [12 empty] | Record in SSDR Segment 2
1994-02-16 02:50 | [12 empty] | Upload Exposure Tables; COOL_EXP
1994-02-16 02:51 | [12 empty] | Upload Sequence Table; DHUSEQ_21
1994-02-16 02:51 | [12 empty] | Upload Sequence Table; SEQ_IRS
1994-02-16 02:51 | [12 empty] | For 40 cycles: Every Minute: DHUSEL31; DHUSEL21
1994-02-16 03:40 | [12 empty] | DHUSELNO
1994-02-16 03:40 | [12 empty] | Upload Sequence table; SEQ_31
End Cooldown Test
Begin Dark field Test
1994-02-16 03:46 | [12 empty] | Record in SSDR Segment 3 | [5 empty] | THIS TEST IS BEING REPEATED SINCE THE IMAGES FROM THE EARLIER RUN WERE NOT SAVED
1994-02-16 03:47 | [12 empty] | Start NIR Darkfields
Upload new NIR Exposure settings every second (20 sets in all)
Take NIR Darkfield Images (DHUSEL18)
DHUSELNO
Turn OFF NIR Camera
Start LWIR Darkfields
Upload new LWIR Exposure settings every second (20 sets in all)
Take LWIR Darkfield images (DHUSEL17)
DHUSEL 1
Turn OFF LWIR Camera
Turn ON Hires and UV/Vis Cameras
1994-02-16 03:59 | [12 empty] | DHUSEL1
Slew S/C (GNC12MZMYRW)
1994-02-16 04:10 | [12 empty] | Close Both Startracker Doors
1994-02-16 04:17 | [12 empty] | Execute STDark (Perform Startracker Dark fields)
1994-02-16 04:18 | [10 empty] | CAN | AOS
Load up new STA Exposure Settings every 6 seconds (18 sets in all)
[13 empty] | Take Startracker A Dark fields (DHUSEL13) | [5 empty] | Uncompressed STA Images
Load up new STB Exposure Settings every 6 seconds (18 sets in all)
[13 empty] | Take Startracker B Darkfields (DHUSEL14) | [5 empty] | Uncompressed STB Images
Activate Startracker A
1994-02-16 04:23 | [12 empty] | Start UV/Vis Darkfields
Upload new UVV Exposure settings every 2 seconds (18 sets in all)
Take Darkfield Images (DHUSEL15)
DHUSEL1
Turn OFF UV/Vis Camera
1994-02-16 04:25 | [12 empty] | Start Hires Darkfields
Upload new Hires Exposure settings every 2 seconds (27 sets in all)
Take Darkfield Images (DHUSEL16)
1994-02-16 04:37 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-16 04:37 | [12 empty] | Turn OFF Hires Camera
1994-02-16 04:59 | [12 empty] | Slew S/C High Gain Antenna to Goldstone Station (GNC13GDSRW)
1994-02-16 05:01 | [12 empty] | Switch to High Gain Transmitter
1994-02-16 05:26 | [12 empty] | DHUSELNO
1994-02-16 05:28 | [12 empty] | Upload New Exposure Settings for Startrackers (STA_350_2_OFF7; STB_350_2_OFF7
1994-02-16 05:31 | [12 empty] | DHUSEL1
1994-02-16 05:39 | [12 empty] | Slew S/C to point High Gain Antenna at Goldstone
End Dark Field Test
1994-02-16 05:45 | [12 empty] | Download SSDR Segment 2
1994-02-16 05:49 | [12 empty] | Download SSDR Segment 2
1994-02-16 05:58 | [10 empty] | PMK | LOS
1994-02-16 06:26 | [12 empty] | Download SSDR Segment 3
1994-02-16 07:17 | [12 empty] | Download SSDR Segment 3
1994-02-16 07:52 | [12 empty] | Slew S/C to point High Gain Antenna to Canberra (GNC13CANRW)
1994-02-16 07:58 | [12 empty] | Switch to Datarate of 8 kbps
1994-02-16 07:59 | [12 empty] | Switch to Omni Transmitter
Begin Full Earth Observation
1994-02-16 08:09 | [12 empty] | Slew S/C to Center Sensors on Full Earth (GNC13JOSHRW)
1994-02-16 08:18 | [12 empty] | Turn on Hires, UV/VIS Cameras
1994-02-16 08:21 | [12 empty] | Record to SSDR Segment 1
1994-02-16 08:23 | [12 empty] | Request UV/Vis Realtime Image, filter 1
1994-02-16 08:25 | [10 empty] | GDS | LOS
1994-02-16 08:31 | [12 empty] | Request UV/Vis Realtime Image, filter 1
1994-02-16 08:35 | [12 empty] | Set Data link rate to 64 kbps
1994-02-16 08:44 | [12 empty] | Set Data link rate back to 8 kpbs
1994-02-16 09:21 | [12 empty] | Upload Sequence Table (EARTHS_SEG_31)
1994-02-16 09:22 | [12 empty] | Upload Exposure Settings (EXPDAYVDB)
1994-02-16 09:25 | [12 empty] | DHUSEL31
1994-02-16 10:09 | [12 empty] | Set Data Rate to 8 kpbs
1994-02-16 10:12 | [12 empty] | DHUSEL1
1994-02-16 10:30 | [12 empty] | Turn OFF UVVIS, Hires
End Full Earth Observation
Prepare for P2 Correction Burn
1994-02-16 10:39 | [12 empty] | Slew S/C to P2 Correction Burn Orientation (GNC12P2CRW)
1994-02-16 10:52 | [12 empty] | Record to SSDR Segment 0
1994-02-16 10:58 | [12 empty] | Slew S/C High Gain Antenna to Canberra (GNC13CANRW)
1994-02-16 11:00 | [12 empty] | Switch to Omni Transmitter
1994-02-16 11:07 | [12 empty] | Close both Startracker Doors
1994-02-16 11:24 | [12 empty] | Switch to High-Gain Transmitter
1994-02-16 12:41 | [10 empty] | MAD | AOS
1994-02-16 12:50 | [12 empty] | Slew S/C to P2 Correction Burn Orientation (GNC12P2CRW)
1994-02-16 12:54 | [12 empty] | P2 Correction Burn
1994-02-16 13:04 | ` | [11 empty] | Slew S/C High Gain Antenna to Canberra (GNC13CANRW)
1994-02-16 13:07 | [12 empty] | Swith to Omni Transmitter
1994-02-16 13:30 | [10 empty] | CAN | LOS
1994-02-16 13:24 | [12 empty] | Switch to High-Gain Transmitter
1994-02-16 13:27 | [12 empty] | Switch to Omni Transmitter
1994-02-16 13:28 | [12 empty] | Slew S/C High Gain Antenna to Goldstone Site (GNC13GDSRW)
1994-02-16 14:42 | [12 empty] | Slew S/C High Gain to Madrid Station (GNC12MADRW)
1994-02-16 14:43 | [12 empty] | Switch to High Gain Transmitter
Open Startracker A Door
1994-02-16 14:45 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-16 15:41 | [12 empty] | Read Dosimeter
1994-02-16 15:46 | [12 empty] | Expose Dosimeter
1995-02-16 15:56 | [12 empty] | Switch to Downlink Rate of 128 kpbs
1994-02-16 16:02 | [12 empty] | Download SSDR Segment 0
Begin Earth Observation #9
1994-02-16 16:56 | [12 empty] | Switch to Omni Transmitter
1994-02-16 17:01 | [12 empty] | Slew S/C to Earth Observation Attitude (GNC12EOF1612)
1994-02-16 17:08 | [12 empty] | Turn ON All Cameras
1994-02-16 17:09 | [12 empty] | Turn off Laser Transmitter
1994-02-16 17:13 | [12 empty] | Open Startracker B Door
1994-02-16 17:14 | [12 empty] | Upload Exposure Paramters (EXPDAY4)
1994-02-16 17:15 | [12 empty] | Upload Sequence Table (SEQ_262)
2/16/194 17:17 | [12 empty] | Initialize Filters (DHUSEL26)
1994-02-16 17:17 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-16 17:17 | [12 empty] | Record to SSDR Segment 1
1994-02-16 17:21 | [12 empty] | DHUSEL10 | [5 empty] | Filter 3
1994-02-16 17:21 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-16 17:27 | [12 empty] | DHUSEL0 | [5 empty] | Compressed & Uncompressed, including Startrackers
1994-02-16 17:27 | [12 empty] | DHUSEL1
1994-02-16 17:29 | [12 empty] | Open Sensor Door
1994-02-16 17:33 | [12 empty] | Request UV Image, filter 4
1994-02-16 17:33 | [12 empty] | DHUSEL0 | [5 empty] | Compressed & Uncompressed, including Startrackers
1994-02-16 17:33 | [10 empty] | PMK | AOS
1994-02-16 17:33 | [12 empty] | DHUSEL1
1994-02-16 17:35 | [12 empty] | Request UV Image, filter 4
1994-02-16 17:35 | [12 empty] | Activate Autoexeposure for UV/VIS, NIR, LWIR Cameras
1994-02-16 17:36 | [12 empty] | DHUSEL0 | [5 empty] | Compressed & Uncompressed, including Startrackers
1994-02-16 17:39 | [12 empty] | Request UV Image, filter 4
1994-02-16 17:39 | [12 empty] | DHUSEL1
1994-02-16 17:42 | [12 empty] | Activate Centroiding for UV/VIS, filter 4, Hires, filter 4, NIR, filter 1
1994-02-16 17:43 | [12 empty] | Request NIR Image, filter 1
1994-02-16 17:43 | [12 empty] | DHUSEL0 | [5 empty] | Compressed & Uncompressed, including Startrackers
1994-02-16 17:48 | [12 empty] | Activate Centroiding for NIR, filter 1, LWIR
1994-02-16 17:45 | [12 empty] | DHUSEL1
1994-02-16 17:48 | [12 empty] | Deactivate Centroiding, all Cameras
1994-02-16 17:49 | [12 empty] | Reset Filter Settings (DHUSEL27
1994-02-16 17:50 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-16 18:00 | [12 empty] | Upload Default Startracker Exposure Settings (STA_3502_OFF7, STB_350_2_OFF7)
1994-02-16 18:04 | [12 empty] | DHUSEL10 | [5 empty] | Filter 3
1994-02-16 18:04 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-16 18:28 | [12 empty] | Turn OFF All Cameras
1994-02-16 18:28 | [12 empty] | Close Sensor Door
1994-02-16 18:36 | [12 empty] | Download SSDR Segment 1
End Earth Observation #9
Begin Moon Observation
1994-02-16 20:21 | [12 empty] | Close Startracker B Door
1994-02-16 20:28 | [12 empty] | Slew S/C to Lunar Pointing (GNC14)
1994-02-16 20:28 | [10 empty] | GDS | AOS
1994-02-16 20:46 | [12 empty] | Turn ON all Cameras
1994-02-16 20:46 | [12 empty] | Turn OFF Laser Transmitter
1994-02-16 20:48 | [12 empty] | Open Sensor Door
1994-02-16 20:56 | [12 empty] | Upload Exposure Paramters (EXPDAY4)
1994-02-16 20:58 | [12 empty] | Upload Sequence Table (SEQ_262)
1994-02-16 20:58 | [12 empty] | Initialize Filters (DHUSEL26)
1994-02-16 20:59 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-16 20:59 | [12 empty] | Record to SSDR Segment 1
1994-02-16 21:00 | [12 empty] | DHUSEL10 | [5 empty] | Filter 3
1994-02-16 21:01 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-16 21:01 | [12 empty] | Request UV Image, Filter 1
1994-02-16 21:02 | [12 empty] | DHUSEL0 | [5 empty] | Compressed & Uncompressed, including Startrackers
1994-02-16 21:02 | [12 empty] | DHUSEL1
1994-02-16 21:05 | [12 empty] | Request UV Image, filter 4
1994-02-16 21:05 | [12 empty] | DHUSEL0 | [5 empty] | Compressed & Uncompressed, including Startrackers
1994-02-16 21:05 | [12 empty] | DHUSEL1
1994-02-16 21:06 | [12 empty] | Activate Autoexposure for UV/VIS, filter 4, NIR, filter 1, LWIR Cameras
1994-02-16 21:07 | [12 empty] | DHUSEL0 | [5 empty] | Compressed & Uncompressed, including Startrackers
1994-02-16 21:08 | [12 empty] | Request UV Image, filter 4
1994-02-16 21:08 | [12 empty] | DHUSEL1
1994-02-16 21:09 | [12 empty] | Activate Centroiding for UV/VIS, filter 4
1994-02-16 21:10 | [12 empty] | DHUSEL0 | [5 empty] | Compressed & Uncompressed, including Startrackers
1994-02-16 21:10 | [12 empty] | Request UV Image, filter 4
1994-02-16 21:11 | [12 empty] | DHUSEL1
1994-02-16 21:12 | [12 empty] | Deactivate Centroiding for UV/VIS
1994-02-16 21:14 | [12 empty] | DHUSEL10
1994-02-16 21:15 | [12 empty] | DHUSEL1
1994-02-16 21:15 | [12 empty] | Upload Default Startracker Exposure Settings (STA_350_2_OFF7, STB_350_2_OFF7)
1994-02-16 21:20 | [12 empty] | DHU Crash/ Reboot
1994-02-16 21:22 | [12 empty] | Turn OFF All Cameras
1994-02-16 21:27 | [12 empty] | Close Sensor Door
End Moon Observation
1994-02-16 21:36 | [12 empty] | Reset DHU
1994-02-16 21:46 | [12 empty] | Upload DHU Code Ver 2.41
2004-02-16 21:56 | [12 empty] | Upload Startracker Sequence Tables (SEQ_01, SEQ_02)
1994-02-16 21:59 | [12 empty] | Run Startracker A (DHUSEL1)
1994-02-16 21:59 | [12 empty] | Run Startracker B (DHUSEL2)
1994-02-16 22:00 | [12 empty] | DHUSEL1
1994-02-16 22:06 | [12 empty] | DHUSELNO
1994-02-16 22:06 | [12 empty] | Upload B_PHASE Sequence Tables
1994-02-16 22:15 | [12 empty] | DHUSEL1
1994-02-16 22:16 | [12 empty] | Turn Ranging A OFF
1994-02-16 22:32 | [12 empty] | Upload A_PHASE Sequence Tables
1994-02-16 22:58 | [12 empty] | Upload DHU Compression Tables
1994-02-16 23:03 | [12 empty] | Turn Ranging B OFF
1994-02-16 23:05 | [12 empty] | Set Data Link Rate to 8 kbps
1994-02-16 23:08 | [12 empty] | Slew S/C High Gain Antenna to Pomonkey Station (GNC13PMKRW)
1994-02-16 23:20 | [12 empty] | Turn ON High Gain Transmitter
1994-02-16 23:21 | [12 empty] | Set Data Link Rate to 128 kbps
1994-02-16 23:24 | [12 empty] | Download SSDR Segment 1