## Sheet1
UTC Time | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-02-17 01:18 | [10 empty] | MAD | LOS
1994-02-17 01:43 | [12 empty] | Read Dosimeter
1994-02-17 01:48 | [12 empty] | Expose Dosimeter
1994-02-17 01:48 | [12 empty] | Resd Dosimeter
1994-02-17 01:53 | [12 empty] | Expose Dosimeter
BEGIN STARTRACKER POINTING TEST
1994-02-17 02:39 | [12 empty] | Turn ON UV/VIS, Hires Cameras | [5 empty] | TEST DID NOT RUN SUCCESSFULLY DUE TO DHU CRASH AND SENSOR DOOR BEING CLOSED
1994-02-17 02:39 | [12 empty] | Record in SSDR Segment 2
1994-02-17 02:44 | [12 empty] | Upload Sequence Table (AEQ_24HU)
1994-02-17 02:58 | [12 empty] | Initialize Filters (DHUSEL26)
1994-02-17 03:00 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-17 03:01 | [12 empty] | Upload Sensor Settings (HSP10)
1994-02-17 03:14 | [12 empty] | Slew S/C to point Cameras toward South Galatic Pole (GNC12SGP28) | [5 empty] | Uncompressed STA Images
1994-02-17 03:18 | [12 empty] | Set Date Rate to 8 kbps
1994-02-17 03:18 | [12 empty] | Switch to Omni Transmitter | [5 empty] | Uncompressed STB Images
1994-02-17 03:27 | [12 empty] | DHUSEL24
1994-02-17 03:28 | [12 empty] | DHU CRASHED
1994-02-17 03:31 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-17 03:56 | [12 empty] | Turn OFF Hires, UV/VIS Cameras
END STARTRACKER POINTING TEST DUE TO DHU CRASH
1994-02-17 03:59 | [12 empty] | RESET DHU
1994-02-17 03:59 | [12 empty] | Upload DHU Software Ver. 2.41
1994-02-17 04:04 | [12 empty] | Upload Startracker Sequence Tables (SEQ_01, SEQ_02)
1994-02-17 04:05 | [12 empty] | Run Startracker A (DHUSEL1)
1994-02-17 04:07 | [12 empty] | Run Startracker B (DHUSEL2)
1994-02-17 04:07 | [12 empty] | DHUSEL1
1994-02-17 04:09 | [12 empty] | DHUSELNO
1994-02-17 04:09 | [12 empty] | Upload B_PHASE Sequence Tables
1994-02-17 04:13 | [12 empty] | Upload A_PHASE Sequence Tables
1994-02-17 04:14 | [12 empty] | Upload DHU Compression Tables
1994-02-17 04:16 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-17 04:37 | [12 empty] | Slew S/C High Gain Antenna to point to Pomonkey Station (GNC13PMKRW)
1994-02-17 04:38 | [10 empty] | CAN | AOS
1994-02-17 04:51 | [12 empty] | Set Data Link Rate to 8 kbps
1994-02-17 04:52 | [12 empty] | Turn OFF All C ameras
1994-02-17 05:12 | [12 empty] | Switch to High Gain Transmitter
1994-02-17 05:20 | [12 empty] | Download SSDR Segment 2
1994-02-17 05:37 | [12 empty] | Upload Sensor Exposure Settings (LUNAREH)
1994-02-17 05:37 | [12 empty] | Upload Sequence Tables (AEQ-15, AEQ_21)
1994-02-17 05:43 | [12 empty] | Turn OFF Transmitter
1994-02-17 06:14 | [10 empty] | PMK | LOS
1994-02-17 08:23 | [12 empty] | Slew S/C High Gain to Canberra Station (GNC13CANRW)
1994-02-17 08:25 | [12 empty] | Switch to High Gain Transmitter
1994-02-17 08:29 | [12 empty] | Turn High Gain Ranging ON, Omni Ranging OFF
1994-02-17 08:30 | [10 empty] | GDS | LOS
1994-02-17 08:31 | [12 empty] | Download SSDR Segment 1
1994-02-17 11:00 | [12 empty] | Turn High Gain Ranging Off
1994-02-17 11:01 | [12 empty] | Switch to Data Link Rate of 8 kbps
1994-02-17 11:10 | [12 empty] | Turn OFF Transmitter
1994-02-17 12:38 | [10 empty] | MAD | AOS
1994-02-17 13:22 | [10 empty] | CAN | LOS
1994-02-17 15:13 | [12 empty] | Turn ON Omni Transmitter
1994-02-17 15:14 | [12 empty] | Turn ON Omni Ranging
BEGIN STARTRACKER POINTING TEST
1994-02-17 15:42 | [12 empty] | Turn ON UV/VIS, Hires Cameras
1994-02-17 15:55 | [12 empty] | Upload Sequences Table (AEQIL_263_HSP, SEQ_24_HSP, AEQ_24HSP)
1994-02-17 15:58 | [12 empty] | Initialize Filters (DHUSEL26)
1994-02-17 15:58 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-17 15:59 | [12 empty] | Record in SSDR Segment 1
1994-02-17 16:03 | [12 empty] | Upload Sensor Settings (HSP10)
1994-02-17 16:19 | [12 empty] | Slew S/C to point Cameras to Betelgeuse (GNC12SGP28)
1994-02-17 16:25 | [12 empty] | OPEN Startracker B Door
1994-02-17 16:29 | [12 empty] | Open Sensor Door
1994-02-17 16:34 | [12 empty] | Request UV/Vis Image
1994-02-17 16:36 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 16:37 | [12 empty] | DHUSEL1
1994-02-17 16:41 | [12 empty] | Request Hires Image
1994-02-17 16:42 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 16:42 | [12 empty] | DHUSEL1
1994-02-17 16:48 | [12 empty] | Request UV Image
1994-02-17 16:49 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 16:49 | [12 empty] | DHUSEL1
1994-02-17 16:51 | [12 empty] | Request UV/VIS Image
1994-02-17 16:52 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 16:52 | [12 empty] | DHUSEL1
1994-02-17 16:57 | [12 empty] | Request UV Image
1994-02-17 16:58 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 16:58 | [12 empty] | DHUSEL1
1994-02-17 17:01 | [12 empty] | Request Hires Image
1994-02-17 17:01 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 17:02 | [12 empty] | DHUSEL1
1994-02-17 17:11 | [12 empty] | Request Hires Image
1994-02-17 17:11 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 17:12 | [12 empty] | DHUSEL1
1994-02-17 17:18 | [12 empty] | Request Hires Image
1994-02-17 17:19 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 17:19 | [12 empty] | DHUSEL1
1994-02-17 17:23 | [12 empty] | Slew S/C to Point Cameras toward Betelgeuse with a roll of 60° (GNC12SGP29)
1994-02-17 17:24 | [10 empty] | PMK | AOS
1994-02-17 17:28 | [12 empty] | Request Hires Image
1994-02-17 17:28 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 17:29 | [12 empty] | DHUSEL1
1994-02-17 17:34 | [12 empty] | Request Hires Image
1994-02-17 17:34 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 17:36 | [12 empty] | DHUSEL1
1994-02-17 17:41 | [12 empty] | Upload Exposure Settings (HSP1)
1994-02-17 17:42 | [12 empty] | Slew S/C to point Cameras toward Rigel (GNC12SGP31)
1994-02-17 17:45 | [12 empty] | Request Hires Image
1994-02-17 17:46 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 17:46 | [12 empty] | DHUSEL1
1994-02-17 17:49 | [12 empty] | Upload Exposure Settings (HSP2)
1994-02-17 17:55 | [12 empty] | Slew S/C to Point Cameras toward Belletrix (GNC12SGP04)
1994-02-17 17:56 | [12 empty] | Request Hires Image
1994-02-17 17:57 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 17:57 | [12 empty] | DHUSEL1
1994-02-17 17:59 | [12 empty] | Turn Omni Ranging OFF
1994-02-17 18:05 | [12 empty] | Request Hires Image
1994-02-17 18:06 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 18:06 | [12 empty] | DHUSEL1
1994-02-17 18:09 | [12 empty] | Slew S/C to Point Cameras toward Pleaides w/Roll of 60° (GNC12SGP08)
1994-02-17 18:10 | [12 empty] | Request Hires Image
1994-02-17 18:12 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 18:12 | [12 empty] | DHUSEL1
1994-02-17 18:15 | [12 empty] | Upload Exposure Settings (HSP5)
1994-02-17 18:16 | [12 empty] | Slew S/C to Point Cameras toward Alnitak (GNC12SGP13)
1994-02-17 18:17 | [12 empty] | Request Hires Image
1994-02-17 18:19 | [12 empty] | DHUSEL24 | [5 empty] | Also Uncompressed Startracker A and B Images
1994-02-17 18:19 | [12 empty] | DHUSEL1
1994-02-17 18:24 | [12 empty] | Set Data Link Rate to 2 kbps
1994-02-17 18:24 | [12 empty] | Close Startracker B Door
1994-02-17 18:25 | [12 empty] | Turn OFF Hires, UV/VIS Cameras
END STARTRACKER POINTING TEST
1994-02-17 18:27 | [12 empty] | Record to SSDR Segment 2
1994-02-17 18:30 | [12 empty] | Close Sensor Door
BEGIN HIGH GAIN ANTENNA TEST
1994-02-17 18:31 | [12 empty] | Load up RF Test Command List
Run RF_TEST_02
Run RF_TEST_01
Turn IMU B OFF
Run RF_TEST_02
Switch to High Gain Antenna Transmitter
Run RF_TEST_03
RUN RF_TEST_04
RUN RF_TEST _05
RUN RF_TEST_06
RUN RF_TEST_07
RUN RF_TEST_08
END HIGH GAIN ANTENNA TEST
1994-02-17 19:41 | [12 empty] | Slew S/C High Gain Antenna to Pomonkey Ground Station (GNC13PMKRW)
1994-02-17 19:48 | [12 empty] | Set Data Link Rate to 128 kbps
Download SSDR Segment 2
Download SSDR Segment 1
1994-02-17 21:50 | [12 empty] | Turn IMU B ON
1994-02-17 22:05 | [12 empty] | Set Data Link Rate to 8 kbps
1994-02-17 22:06 | [12 empty] | Swtich to Omni Transmitter
1994-02-17 23:12 | [12 empty] | Read Dosimeter
1994-02-17 23:17 | [12 empty] | Expose Dosimeter
BEGIN LUNAR MAPPING REHEARSAL
1994-02-17 21:20 | [12 empty] | Upload Script for Lunar Mapping Rehearsal (LM_SETUP)
1994-02-17 22:00 | [12 empty] | EXECUTE Lunar Mapping Script
1994-02-17 22:00 | [12 empty] | Turn ON NIR and LWIR Cameras
1994-02-17 22:10 | [12 empty] | Turn ON Laser Heater
1994-02-17 22:15 | [12 empty] | Slew to South Galatic Pole (GNC18IDXIRW)
1994-02-17 22:20 | [12 empty] | Open Sensor Door
1994-02-17 22:20 | [12 empty] | Turn on UV/VIS, Hires Cameras
1994-02-17 20:29 | [10 empty] | GDS | AOS
1994-02-17 22:30 | [12 empty] | Initizlied Filter Wheels (DHUSEL26)
1994-02-17 22:30 | [12 empty] | Record to SSDR Segment 5
1994-02-17 22:31 | [12 empty] | Execute LWIR, NIR Dark field Imaging (DHUSEL25)
1994-02-17 22:31 | [12 empty] | DHUSEL31
1994-02-17 22:31 | [12 empty] | Turn ON Laser Transmitter
1994-02-17 22:31 | [12 empty] | DHUSEL1
1994-02-17 22:31 | [12 empty] | Slew to Nadir Pointing (GNC14POSRW)
1994-02-17 22:36 | [12 empty] | Re-initialize filters (DHUSEL26)
1994-02-17 22:37 | [12 empty] | DHUSEL8
1994-02-17 22:40 | [12 empty] | LOAD EXPOSURE TABLES (LUNREH_LAS)
1994-02-17 22:41 | [12 empty] | DHUSEL5
1994-02-17 22:45 | [12 empty] | DHUSEL1
1994-02-17 22:47 | [12 empty] | Load Exposure Table (LUNAREH)
1994-02-17 22:47 | [12 empty] | Turn OFF Laser
1994-02-17 22:47 | [12 empty] | Close Sensor Door
1994-02-17 22:58 | [12 empty] | Goto to Inertial Pointing (GNC12LM1)
1994-02-17 22:59 | [12 empty] | Activate Lunar Exposure for UV/VIS, NIR, LWIR)
1994-02-17 23:01 | [12 empty] | Slew to Nadir Pointing (GNC14POSRW)
1994-02-17 23:03 | [12 empty] | Record to SSDR Segment 6
1994-02-17 23:03 | [12 empty] | Re-initialize filters (DHUSEL26)
1994-02-17 23:04 | [12 empty] | DHUSEL11
1994-02-17 23:08 | [12 empty] | DHUSEL1
1994-02-17 23:10 | [12 empty] | DHUSEL12
1994-02-17 23:15 | [12 empty] | DHUSEL1
1994-02-17 23:19 | [12 empty] | DHUSEL11
1994-02-17 23:23 | [12 empty] | DHUSEL1
1994-02-17 23:29 | [12 empty] | DHUSEL12
1994-02-17 23:33 | [12 empty] | DHUSEL1
1994-02-17 23:40 | [12 empty] | DHUSEL11
1994-02-17 23:47 | [12 empty] | DHUSEL1
1994-02-17 23:56 | [12 empty] | DHUSEL12
DHUSEL1
1994-02-18 00:05 | [12 empty] | Turn OFF UV/VIS, Hires Cameras
1994-02-18 00:05 | [12 empty] | Slew S/C to Point Cameras to Pleiades (GNC18IDX2RW)
1994-02-18 00:09 | [12 empty] | LWIR, NIR Dark fields (DHUSEL25)
1994-02-18 00:09 | [12 empty] | DHUSEL31
1994-02-18 00:10 | [12 empty] | DHUSEL1
1994-02-18 00:10 | [12 empty] | Turn OFF LWIR, NIR Cameras
1994-02-18 00:10 | [12 empty] | Slew High Gain Antenna to Pomonkey Station (GNC13PMKRW)
END LUNAR MAPPING REHEARSAL