## Sheet1
UTC Time | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-02-19 | [12 empty] | Preparing for Lunar Orbit Insertion (LOI1) Burn
1994-02-19 00:16 | [12 empty] | Set Data Link Rate to 8 kbps
1994-02-19 00:49 | [12 empty] | Build Command Set for LOI
1994-02-19 00:50 | [10 empty] | GDS | AOS
1994-02-19 01:00 | [12 empty] | Slew S/C to LOI Burn Orientation
1994-02-19 01:02 | [12 empty] | Switch to Omni Transmitters
1994-02-19 01:02 | [12 empty] | Turn High Gain Ranging OFF
1994-02-19 01:10 | [12 empty] | Open Startracker B Cover
1994-02-19 01:14 | [12 empty] | Turn Omni Ranging ON
1994-02-19 01:15 | [12 empty] | Activate Startracker B (DHUSEL2)
1994-02-19 01:16 | [12 empty] | Close Startracker A Cover
1994-02-19 05:35 | [10 empty] | CAN | AOS
1994-02-19 06:29 | [12 empty] | Open Startracker A Cover
1994-02-19 08:30 | [12 empty] | Activate Startracker A (DHUSEL1)
1994-02-19 08:31 | [12 empty] | Close Startracker B Cover
1994-02-19 08:51 | [12 empty] | Turn OFF Laser Transmitter Heater
1994-02-19 08:57 | [12 empty] | Upload and Schedule LOI Burn Script
1994-02-19 10:08 | [12 empty] | Slew S/C to Updated LOI Attitude (GNC12LOIRW)
1994-02-19 10:19 | [12 empty] | Close Startracker A Door
1994-02-19 10:20 | [12 empty] | DHUSELNO
1994-02-19 10:22 | [12 empty] | Open Startracker B Door
1994-02-19 10:28 | [12 empty] | Activate Startracker B (DHUSEL2)
1994-02-19 11:14 | [12 empty] | Record TLM in SSDR Segment 0
1994-02-19 12:20 | [10 empty] | MAD | AOS
1994-02-19 12:53 | [12 empty] | LUNAR INSERTION BURN | [5 empty] | LUNAR INSERTION BURN
END Loop Timelines