## Sheet1
UTC Time | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-05-06 | 0:00 | [11 empty] | Flat Field Test is planned | [5 empty] | No scheduled SCL scripts, all ground commands.
1994-05-06 03:06 | 3:06 | [9 empty] | MAD | AOS
1994-05-06 03:51 | 3:51 | [9 empty] | CAN | LOS | [6 empty] | 10 Min Coverage gap
Flat Field and Autoexposure Test
1994-05-06 06:01 | 6:01 | [11 empty] | All cameras ON | [5 empty] | S/C is to point the +Z axis to within 5 degree from the Sun, where images will be taken of the inside of the closed sensor door.
1994-05-06 06:17 | 6:17 | [11 empty] | Set downlink rate to 2 Kbps
1994-05-06 06:19 | 6:19 | [11 empty] | Slew s/c Sensors to 5 degrees off axis from Sun (SAFERW) | [5 empty] | Sensor door is closed, at the end of the slew, warming of the door apparently caused the door to warp, giveing a false 'open' indication. Onboard software then fired jets to attempt to remove the Sun from the sensor FOV.
1994-05-06 06:23 | 6:23 | [11 empty] | Record in SSDR Segment 1
1994-05-06 06:24 | 6:24 | [11 empty] | Load Exposure Table (LUNARZ85S) (LUNVEGA)
1994-05-06 06:26 | 6:26 | [11 empty] | DHUSEL29 | [5 empty] | UV Uncompressed
1994-05-06 06:26 | 6:26 | [11 empty] | DHUSEL31 | [5 empty] | NIR Uncompressed
1994-05-06 06:27 | 6:27 | [11 empty] | Activate ST-B (DHUSEL2);
1994-05-06 06:29 | 6:29 | [11 empty] | Load Exposure Table (EARTH_VIEW_AXIS)
1994-05-06 06:30 | 6:30 | [11 empty] | DHUSEL16 | [5 empty] | UV and NIR Compressed
1994-05-06 06:31 | 6:31 | [11 empty] | Activate ST-B (DHUSEL2);
1994-05-06 06:32 | 6:32 | [11 empty] | Slew s/c Sensors to Earth (SAFERW)
1994-05-06 06:38 | 6:38 | [11 empty] | Open sensor door
1994-05-06 06:40 | 6:40 | [11 empty] | Enable auto-exposure
1994-05-06 06:54 | 6:54 | [11 empty] | Initialize filters (DHUSEL26)
1994-05-06 06:55 | 6:55 | [11 empty] | DHUSEL22 | [5 empty] | All Sensors Compressed
1994-05-06 06:58 | 6:58 | [11 empty] | PARK filters (DHUSEL27); Activate ST-B (DHUSEL2);
1994-05-06 07:09 | 7:09 | [11 empty] | All cameras OFF
1994-05-06 08:06 | 8:06 | [9 empty] | PMK | AOS
1994-05-06 10:56 | 10:56 | [9 empty] | GDS | AOS
1994-05-06 11:18 | 11:18 | [11 empty] | Slew s/c HGA to Earth (GNC13EARTH)
End Flat Field and Autoexposure Test
1994-05-06 11:23 | 11:23 | [11 empty] | Switch to DHU mode @ 128 kbps
1994-05-06 11:48 | 11:48 | [11 empty] | Downlink SSDR Segment 1
1994-05-06 14:47 | 14:47 | [9 empty] | MAD | LOS
1994-05-06 18:26 | 18:26 | [9 empty] | CAN | AOS
1994-05-06 18:32 | 18:32 | [11 empty] | Ranging A OFF Ranging B OFF
1994-05-06 20:12 | 20:12 | [9 empty] | PMK | LOS | [6 empty] | 2hr 20 Min Coverage gap
1994-05-06 22:56 | 22:56 | [9 empty] | GDS | LOS | [6 empty] | 2hr 20 Min Coverage gap
1994-05-06 22:41 | 22:41 | [11 empty] | Update state vector (GNC53_06MAY2000)
1994-05-06 23:45 | 23:45 | [11 empty] | Ranging B ON