## Sheet1
UTC Time | Orbit Time (h:mm:ss) | Time Since Previous Event (sec) | Lat. (deg) | Long. (deg) | Altitude (km) | POMONKEY | GOLDSTONE | CANBERRA | MADRID | Sun Shadow | Site | Orbital Event | S/C Command Activities | UV/Vis | HiRes | NIR | LWIR | Laser | Comment
1994-05-07 00:56 | [12 empty] | Turn ON Omni Ranging
1994-05-07 02:54 | [12 empty] | Swtich to Omni
1994-05-07 03:23 | [12 empty] | Slew S/C to point High Gain Antenna toward Earth
1994-05-07 03:25 | [12 empty] | Switch to High Gain Transmitter
1994-05-07 04:01 | [12 empty] | Switch to Omni Transmitter
BEGIN EARTH MOSAIC TEST
1994-05-07 04:03 | [12 empty] | Upload Sequence Tables (MOS_HIRES, MOS_UV_NIR)
1994-05-07 04:05 | [12 empty] | Upload Exposure Settings (EARTH_VIEW_ZAXIS)
1994-05-07 04:12 | [10 empty] | MAD | AOS
1994-05-07 04:17 | [12 empty] | Slew S/C to Point Sensors to Earth (GNC12)
1994-05-07 04:19 | [12 empty] | Reccord to SSDR Segment 1
1994-05-07 04:22 | [12 empty] | DHUSEL16 | [5 empty] | No Data
1994-05-07 04:23 | [12 empty] | Activate Startracker B (DHUSEL2)
1994-05-07 04:23 | [12 empty] | Turn ON UV/VIS, Hires Cameras
1994-05-07 04:25 | [12 empty] | DHUSEL16
1994-05-07 04:30 | [12 empty] | DHUSEL17
1994-05-07 04:36 | [12 empty] | Activate Startracker B (DHUSEL2)
1994-05-07 04:36 | [12 empty] | Slew S/C High Gain Antenna toward Earth
1994-05-07 04:39 | [12 empty] | Switch to High Gain Transmitter
1994-05-07 04:44 | [12 empty] | Download Segment 1
Set Data Link Rate to 8 kbps
Switch to Omni Transmitter
1994-05-07 04:54 | [10 empty] | CAN | LOS | [6 empty] | 10 Min Coverage gap
1994-05-07 04:59 | [12 empty] | Switch to High Gain Transmitter
1994-05-07 05:54 | [12 empty] | Set Data Link Rate to 64 kbps
END EARTH OBSERVATIONS
1994-05-07 07:20 | [12 empty] | Switch to Omni Transmitter
1994-05-07 07:20 | [12 empty] | Set Data Link Rate to 8 kbps
1994-05-07 07:48 | [12 empty] | Slew S/C to Point High Gain Antenna toward Earth
1994-05-07 08:35 | [12 empty] | Download SSDR Segment 1
1994-05-07 09:35 | [10 empty] | PMK | AOS
1994-05-07 09:40 | [12 empty] | Switch to Omni Transmitter
BEGIN EARTH MOSAIC TEST #2
1994-05-07 09:47 | [12 empty] | Slew S/C to Point Cameras toward Earth
1994-05-07 09:51 | [12 empty] | Upload Exposure Settings (EARTH_VIEW_ZAXIS)
1994-05-07 09:52 | [12 empty] | Turn ON NIR, LWIR Cameras
1994-05-07 09:56 | [12 empty] | Record to SSDR Segment 2
1994-05-07 09:58 | [12 empty] | Set Filter Wheels (DHUSEL28)
1994-05-07 09:59 | [12 empty] | DHUSEL16
1994-05-07 10:04 | [12 empty] | DHUSEL17
1994-05-07 10:09 | [12 empty] | Reset Filter Wheels (DHUSEL27)
1994-05-07 10:10 | [12 empty] | Activate Startracker B (DHUSEL2)
1994-05-07 10:11 | [12 empty] | Slew S/C to Point High Gain toward Earth
1994-05-07 10:13 | [12 empty] | Switch to High Gain Transmitter
1994-05-07 10:24 | [12 empty] | Download Segment 1
1994-05-07 10:31 | [12 empty] | Download Segment 2
1994-05-07 10:30 | [12 empty] | Turn OFF LWIR, UVVIS, Hires, NIR
1994-05-07 10:43 | [12 empty] | Set Data Rate to 2 kbps
1994-05-07 10:43 | [12 empty] | Slew S/C to Point Cameras toward Earth
1994-05-07 10:43 | [12 empty] | Switch to Omni Transmitter
END EARTH MOSAIC TEST #2
BEGIN CENTROIDING/TRACKING TEST WITH MOON
1994-05-07 11:51 | [12 empty] | Upload Sequence Table (MEQ_UV_B)
1994-05-07 11:51 | [12 empty] | Upload Exposure Parameters (LUNARZ85S)
1994-05-07 12:13 | [12 empty] | Set Data Link Rate to 64 kbps
1994-05-07 12:16 | [12 empty] | Slew S/C to point Cameras toward Moon
1994-05-07 12:16 | [12 empty] | Switch to Omni Transmitter
1994-05-07 12:18 | [12 empty] | Turn ON UVVIS Camera
1994-05-07 12:20 | [12 empty] | Record to SSDR Segment 3
1994-05-07 12:26 | [12 empty] | DHUSEL9
1994-05-07 12:30 | [12 empty] | Request UV Imag, filter 4
1994-05-07 12:48 | [12 empty] | DHUSEL2
1994-05-07 12:54 | [12 empty] | Download SSDR Segment 3
1994-05-07 12:56 | [10 empty] | GDS | AOS
1994-05-07 12:59 | [12 empty] | Record to SSDR Segment 3
1994-05-07 13:00 | [12 empty] | DHUSEL9
1994-05-07 13:07 | [12 empty] | DHUSEL2
1994-05-07 13:07 | [12 empty] | Upload Sequence Table (MEQ_UV_B)
1994-05-07 13:08 | [12 empty] | DHUSEL9
1994-05-07 13:15 | [12 empty] | DHUSEL2
1994-05-07 13:17 | [12 empty] | Upload Exposure Settings (LUNARZ85S)
1994-05-07 13:18 | [12 empty] | DHUSEL9
PROCESSOR CRASH
CRASH OF HKP
DURING SHORT LOSS OF CONTACT ACS JETS FIRED, EXHAUSTING ATTITUDE & CONTROL FUEL SUPPLY, LEAVING S/C TUMBLING AT 80 REV/MIN.
IMAGES SHOW START OF TUMBLE, RUN UNTIL 13:42
1994-05-07 13:58 | [12 empty] | RESET HKP
RESET DHU
1994-05-07 14:04 | [12 empty] | Upload DHU Code Ver. 2.49
1994-05-07 14:08 | [12 empty] | Upload Sequence Table Set M
1994-05-07 14:12 | [12 empty] | Upload DHU Compression Tables
1994-05-07 14:15 | [12 empty] | Upload Exposure Settings (EXPDAY5)
1994-05-07 14:20 | [12 empty] | Activate Startracker B (DHUSEL2)
1994-05-07 14:29 | [12 empty] | TURN OFF and ON IMU B
1994-05-07 14:39 | [12 empty] | Reset Filter Wheels (DHUSEL28)
1994-05-07 14:39 | [12 empty] | Activate Startracker B (DHUSEL2)
1994-05-07 14:39 | [12 empty] | Reset Filter Wheels (DHUSEL27)
1994-05-07 14:40 | [12 empty] | Activate Startracker B (DHUSEL2)
1994-05-07 14:53 | [12 empty] | DHUSELNO
1994-05-07 14:54 | [12 empty] | Turn OFF Startracker A and B
1994-05-07 15:55 | [12 empty] | Download SSDR Segment 3
1994-05-07 16:02 | [12 empty] | Download SSDR Segment 1
1994-05-07 16:03 | [12 empty] | Download SSDR Segment 3
1994-05-07 16:15 | [12 empty] | Download SSDR Segment 3
1994-05-07 17:01 | [12 empty] | Download SSDR Segment 1
1994-05-07 17:18 | [12 empty] | Download SSDR Segment 2
1994-05-07 17:30 | [12 empty] | Turn OFF Laser Heater
1994-05-07 17:33 | [12 empty] | Download SSDR Segment 3
1994-05-07 19:03 | [12 empty] | Download last part of Segment 3
1994-05-07 19:05 | [10 empty] | MAD | LOS
1994-05-07 19:47 | [12 empty] | Turn ON Hires, UV/VIS, NIR Cameras
1994-05-07 19:47 | [12 empty] | Reset Filter Wheels (DHUSEL27)
1994-05-07 19:47 | [12 empty] | DHUSELNO
1994-05-07 19:47 | [12 empty] | Turn OFF Hires, UV/VIS, NIR Cameras
1994-05-07 21:04 | [12 empty] | Upload Seguence Table (SEQ_ST32)
1994-05-07 21:06 | [12 empty] | Turn ON Startracker A & B
1994-05-07 21:07 | [12 empty] | Record to SSDR Segment 4
1994-05-07 21:08 | [12 empty] | DHUSEL21 | [5 empty] | Uncompressed Startracker A & B Images
1994-05-07 21:12 | [12 empty] | DHUSELNO
1994-05-07 21:12 | [12 empty] | Turn OFF Startracker A & B
1994-05-07 21:13 | [12 empty] | Download SSDR Segment 4
1994-05-07 23:54 | [12 empty] | Upload Sequence Table (SEQ_STS3)
1994-05-07 23:54 | [12 empty] | Turn ON Startracker B
1994-05-07 23:54 | [12 empty] | DHUSEL22 | [5 empty] | Uncompressed Startracker B Images
1994-05-07 23:55 | [12 empty] | DHUSELNO
1994-05-07 23:56 | [12 empty] | Record to SSDR Segment 5
1994-05-07 23:57 | [12 empty] | DHUSEL22 | [5 empty] | Uncompressed Startracker B Images
1994-05-07 23:57 | [12 empty] | DHUSELNO
1994-05-07 23:58 | [12 empty] | Turn OFF Startracker B
1994-05-08 00:04 | [12 empty] | Download SSDR Segment 5